## Background and Preparation
Test protocol "Braille in DAISY Pipeline 2"
Purpose
The purpose of the test protocol and test cases are to report and verify the end-to-end system level functionality vs. the requirements. Test results are tracked through Pass/Fail verdicts against Expected result with supporting Comments and Priorities for failed test cases.
References
Requirements:
https://drive.google.com/drive/folders/0B_Q0CSMAbmEdeHFhMDBfeUJPaHM
http://dev.pef-format.org/dp2/master/index.xhtml
Software build + release notes:
https://github.com/snaekobbi/system/releases
Preconditions
Test server environment configured and ready including integrated pipeline and braille modules:
http://158.39.20.55
Test data prepared.
Agency specific stylesheets defined.
Preparations
System installation: 1. Create and Configure Administrative account for Web UI 2. Connect Web UI to the Pipeline 2 engine Web API 3. Set content / test data storage directories Tester login: 1. Visit Web UI/Test server login page 2. Enter E-mail/UserID and Password 3. Click Login 4. Click Get started
Priority Guideline
P1 (High): To be fixed in the current sprint, next iteration P2 (Medium): To be fixed in the next sprint P3 (Low): To be fixed in a future sprint

## Sprint_6 Test cases_DE
Test protocol "Braille in DAISY Pipeline 2"
Tester: | Mischa Künzle | Software build and release notes: | v1.4.0 | https://github.com/snaekobbi/system/releases/tag/v1.4.0
Country: | Switzerland | Requirements version: | v1.4 | https://github.com/snaekobbi/requirements/releases/tag/v1.4
Date: | 2012-12-21 | CSS Specification: |  | http://snaekobbi.github.io/braille-css-spec/master/index.html
|  | Template User Guide: |  | https://github.com/daisy/pipeline-webui/wiki/Templating
Test Case 4.3:36, Support for Double letter spacing
Requirement ID: | 4.3:36 | http://snaekobbi.github.io/requirements/v1.4/#4.3:36
Description: | The system shall support double letter spacing, meaning adding a space between characters. Some characters should be kept together such as a capital sign and a letter. (4.3:36) | Example: https://github.com/snaekobbi/pipeline-mod-celia/blob/6a3a50e586e31b12947fba6406baa3dcb9ac548f/src/test/xprocspec/test_css_formatter.xprocspec
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | FI
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. set Optional parameters 5. click "Start job" 6. see storage Result/Output Directory file 7.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. set Optional parameters 5. click Start job 6. see storage Result/Output Directory file 7. verify output result | Transformer query: fi: (formatter:dotify)(translator:celia) CSS Specification details: http://snaekobbi.github.io/braille-css-spec/#word-spacing-the-word-spacing-property http://snaekobbi.github.io/braille-css-spec/#h3_letter-spacing-the-letter-spacing-property
Expected result: | FI
Comments:
Pass/Fail:
Agency Priority: | (See Priority Guideline in "Background and Preparation" TAB)
Test Case 4.5:78, Support for User control over page breaking
Requirement ID: | 4.5:78 | http://snaekobbi.github.io/requirements/v1.4/#4.5:78
Description: | The user shall have control over page breaking by means of •inserting hard page breaks, •protecting blocks from being split across multiple pages, •avoiding page breaks within blocks leaving only the first line(s) on the first page (orphan control), •avoiding page breaks within blocks leaving only the last line(s) on the second page (widow control), and •keeping a block’s first line(s) on the same page as the preceding block. (4.5:78)
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | DE
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. set Optional parameters 5. click "Start job" 6. see storage Result/Output Directory file 7.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. set Optional parameters 5. click Start job 6. see storage Result/Output Directory file 7. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result: | DE
Comments:
Pass/Fail: | pass
Agency Priority: | (See Priority Guideline in "Background and Preparation" TAB)
Test Case 4.7:102, Support for generated content (variables, counters)
Requirement ID: | 4.7:102 | http://snaekobbi.github.io/requirements/v1.4/#4.7:102
Description: | The system shall be able to evaluate certain variables and counters at so-called "fields", for example on the title page or in the page header or footer. Supported variables shall include at least the current braille page number, the current print page number or range of print pages contained in the current braille page, the current volume number, the total number of volumes, the total number of braille pages or sheets contained in the current volume or book, the current chapter title, the current chapter number, and the date. (4.7:102)
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | DE, DK, NL
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. set Optional parameters 5. click "Start job" 6. see storage Result/Output Directory file 7.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. set Optional parameters 5. click Start job 6. see storage Result/Output Directory file 7. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2) dk: (formatter:dotify)(translator:nota)(grade:1¦2) nl: (formatter:dotify)(translator:dedicon)
Expected result: | DE
DK
NL
Comments:
Pass/Fail:
Agency Priority: | (See Priority Guideline in "Background and Preparation" TAB)
Test Case 4.8:106, Support for Possibility of rendering print page breaks
Requirement ID: | 4.8:106 | http://snaekobbi.github.io/requirements/v1.4/#4.8:106
Description: | The system shall provide the possibility of rendering print page breaks as marks in the left margin, taking them out of the normal text flow so that text that follows the element can continue on the same line. (4.8:106) | Example: https://github.com/snaekobbi/pipeline-mod-nlb/blob/aa3d6a629169074c69a0053d999c267af3bb499d/src/test/xprocspec/test_css_formatter.xprocspec
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | NO
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. set Optional parameters 5. click "Start job" 6. see storage Result/Output Directory file 7.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. set Optional parameters 5. click Start job 6. see storage Result/Output Directory file 7. verify output result | Transformer query: no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3)
Expected result: | NO
Comments:
Pass/Fail:
Priority: | (See Priority Guideline in Background and Preparation TAB)

## Sprint_6 Test cases_FI
Test protocol "Braille in DAISY Pipeline 2"
Tester: |  | Software build and release notes: | v1.4.0 | https://github.com/snaekobbi/system/releases/tag/v1.4.0
Country: |  | Requirements version: | v1.4 | https://github.com/snaekobbi/requirements/releases/tag/v1.4
Date: |  | CSS Specification: |  | http://snaekobbi.github.io/braille-css-spec/master/index.html
|  | Template User Guide: |  | https://github.com/daisy/pipeline-webui/wiki/Templating
Test Case 4.3:36, Support for Double letter spacing
Requirement ID: | 4.3:36 | http://snaekobbi.github.io/requirements/v1.4/#4.3:36
Description: | The system shall support double letter spacing, meaning adding a space between characters. Some characters should be kept together such as a capital sign and a letter. (4.3:36) | Example: https://github.com/snaekobbi/pipeline-mod-celia/blob/6a3a50e586e31b12947fba6406baa3dcb9ac548f/src/test/xprocspec/test_css_formatter.xprocspec
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | FI
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. set Optional parameters 5. click "Start job" 6. see storage Result/Output Directory file 7.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. set Optional parameters 5. click Start job 6. see storage Result/Output Directory file 7. verify output result | Transformer query: fi: (formatter:dotify)(translator:celia) CSS Specification details: http://snaekobbi.github.io/braille-css-spec/#word-spacing-the-word-spacing-property http://snaekobbi.github.io/braille-css-spec/#h3_letter-spacing-the-letter-spacing-property
Expected result: | FI
Comments: | Double letter spacing works as defined but another problem arises: with this option we choose not to use hyphenating. But with double spacing the words can be longer than the line lenght. Then we would prefer forced hyphenating rather than the word overflowing uncontrollably to the next line. The users are little children so it is too confusing. Is this possible?
Pass/Fail: | Pass
Agency Priority: | (See Priority Guideline in "Background and Preparation" TAB)
Test Case 4.5:78, Support for User control over page breaking
Requirement ID: | 4.5:78 | http://snaekobbi.github.io/requirements/v1.4/#4.5:78
Description: | The user shall have control over page breaking by means of •inserting hard page breaks, •protecting blocks from being split across multiple pages, •avoiding page breaks within blocks leaving only the first line(s) on the first page (orphan control), •avoiding page breaks within blocks leaving only the last line(s) on the second page (widow control), and •keeping a block’s first line(s) on the same page as the preceding block. (4.5:78)
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | DE
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. set Optional parameters 5. click "Start job" 6. see storage Result/Output Directory file 7.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. set Optional parameters 5. click Start job 6. see storage Result/Output Directory file 7. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result: | DE
Comments:
Pass/Fail:
Agency Priority: | (See Priority Guideline in "Background and Preparation" TAB)
Test Case 4.7:102, Support for generated content (variables, counters)
Requirement ID: | 4.7:102 | http://snaekobbi.github.io/requirements/v1.4/#4.7:102
Description: | The system shall be able to evaluate certain variables and counters at so-called "fields", for example on the title page or in the page header or footer. Supported variables shall include at least the current braille page number, the current print page number or range of print pages contained in the current braille page, the current volume number, the total number of volumes, the total number of braille pages or sheets contained in the current volume or book, the current chapter title, the current chapter number, and the date. (4.7:102)
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | DE, DK, NL
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. set Optional parameters 5. click "Start job" 6. see storage Result/Output Directory file 7.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. set Optional parameters 5. click Start job 6. see storage Result/Output Directory file 7. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2) dk: (formatter:dotify)(translator:nota)(grade:1¦2) nl: (formatter:dotify)(translator:dedicon)
Expected result: | DE
DK
NL
Comments:
Pass/Fail:
Agency Priority: | (See Priority Guideline in "Background and Preparation" TAB)
Test Case 4.8:106, Support for Possibility of rendering print page breaks
Requirement ID: | 4.8:106 | http://snaekobbi.github.io/requirements/v1.4/#4.8:106
Description: | The system shall provide the possibility of rendering print page breaks as marks in the left margin, taking them out of the normal text flow so that text that follows the element can continue on the same line. (4.8:106) | Example: https://github.com/snaekobbi/pipeline-mod-nlb/blob/aa3d6a629169074c69a0053d999c267af3bb499d/src/test/xprocspec/test_css_formatter.xprocspec
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | NO
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. set Optional parameters 5. click "Start job" 6. see storage Result/Output Directory file 7.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. set Optional parameters 5. click Start job 6. see storage Result/Output Directory file 7. verify output result | Transformer query: no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3)
Expected result: | NO
Comments:
Pass/Fail:
Priority: | (See Priority Guideline in Background and Preparation TAB)

## Sprint_6 Test cases_NO
Test protocol "Braille in DAISY Pipeline 2"
Tester: |  | Software build and release notes: | v1.4.0 | https://github.com/snaekobbi/system/releases/tag/v1.4.0
Country: |  | Requirements version: | v1.4 | https://github.com/snaekobbi/requirements/releases/tag/v1.4
Date: |  | CSS Specification: |  | http://snaekobbi.github.io/braille-css-spec/master/index.html
|  | Template User Guide: |  | https://github.com/daisy/pipeline-webui/wiki/Templating
Test Case 4.3:36, Support for Double letter spacing
Requirement ID: | 4.3:36 | http://snaekobbi.github.io/requirements/v1.4/#4.3:36
Description: | The system shall support double letter spacing, meaning adding a space between characters. Some characters should be kept together such as a capital sign and a letter. (4.3:36) | Example: https://github.com/snaekobbi/pipeline-mod-celia/blob/6a3a50e586e31b12947fba6406baa3dcb9ac548f/src/test/xprocspec/test_css_formatter.xprocspec
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | FI
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. set Optional parameters 5. click "Start job" 6. see storage Result/Output Directory file 7.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. set Optional parameters 5. click Start job 6. see storage Result/Output Directory file 7. verify output result | Transformer query: fi: (formatter:dotify)(translator:celia) CSS Specification details: http://snaekobbi.github.io/braille-css-spec/#word-spacing-the-word-spacing-property http://snaekobbi.github.io/braille-css-spec/#h3_letter-spacing-the-letter-spacing-property
Expected result: | FI
Comments:
Pass/Fail:
Agency Priority: | (See Priority Guideline in "Background and Preparation" TAB)
Test Case 4.5:78, Support for User control over page breaking
Requirement ID: | 4.5:78 | http://snaekobbi.github.io/requirements/v1.4/#4.5:78
Description: | The user shall have control over page breaking by means of •inserting hard page breaks, •protecting blocks from being split across multiple pages, •avoiding page breaks within blocks leaving only the first line(s) on the first page (orphan control), •avoiding page breaks within blocks leaving only the last line(s) on the second page (widow control), and •keeping a block’s first line(s) on the same page as the preceding block. (4.5:78)
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | DE
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. set Optional parameters 5. click "Start job" 6. see storage Result/Output Directory file 7.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. set Optional parameters 5. click Start job 6. see storage Result/Output Directory file 7. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result: | DE
Comments:
Pass/Fail:
Agency Priority: | (See Priority Guideline in "Background and Preparation" TAB)
Test Case 4.7:102, Support for generated content (variables, counters)
Requirement ID: | 4.7:102 | http://snaekobbi.github.io/requirements/v1.4/#4.7:102
Description: | The system shall be able to evaluate certain variables and counters at so-called "fields", for example on the title page or in the page header or footer. Supported variables shall include at least the current braille page number, the current print page number or range of print pages contained in the current braille page, the current volume number, the total number of volumes, the total number of braille pages or sheets contained in the current volume or book, the current chapter title, the current chapter number, and the date. (4.7:102)
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | DE, DK, NL
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. set Optional parameters 5. click "Start job" 6. see storage Result/Output Directory file 7.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. set Optional parameters 5. click Start job 6. see storage Result/Output Directory file 7. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2) dk: (formatter:dotify)(translator:nota)(grade:1¦2) nl: (formatter:dotify)(translator:dedicon)
Expected result: | DE
DK
NL
Comments:
Pass/Fail:
Agency Priority: | (See Priority Guideline in "Background and Preparation" TAB)
Test Case 4.8:106, Support for Possibility of rendering print page breaks
Requirement ID: | 4.8:106 | http://snaekobbi.github.io/requirements/v1.4/#4.8:106
Description: | The system shall provide the possibility of rendering print page breaks as marks in the left margin, taking them out of the normal text flow so that text that follows the element can continue on the same line. (4.8:106) | Example: https://github.com/snaekobbi/pipeline-mod-nlb/blob/aa3d6a629169074c69a0053d999c267af3bb499d/src/test/xprocspec/test_css_formatter.xprocspec
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | NO
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. set Optional parameters 5. click "Start job" 6. see storage Result/Output Directory file 7.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. set Optional parameters 5. click Start job 6. see storage Result/Output Directory file 7. verify output result | Transformer query: no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3)
Expected result: | NO
Comments:
Pass/Fail: | Pass
Priority: | (See Priority Guideline in Background and Preparation TAB)