## Background and Preparation
Test protocol "Braille in DAISY Pipeline 2"
Purpose
The purpose of the test protocol and test cases are to report and verify the end-to-end system level functionality vs. the requirements. Test results are tracked through Pass/Fail verdicts against Expected result with supporting Comments for failed test cases.
References
Requirements:
https://drive.google.com/drive/folders/0B_Q0CSMAbmEdeHFhMDBfeUJPaHM
http://dev.pef-format.org/dp2/master/index.xhtml
Software build + release notes:
https://github.com/snaekobbi/system/releases
Preconditions
Test server environment configured and ready including integrated pipeline and braille modules:
http://158.39.20.55
Test data prepared.
Agency specific stylesheets defined.
Preparations
System installation: 1. Create and Configure Administrative account for Web UI 2. Connect Web UI to the Pipeline 2 engine Web API 3. Set content / test data storage directories Tester login: 1. Visit Web UI/Test server login page 2. Enter E-mail/UserID and Password 3. Click Login 4. Click Get started

## Sprint_3 Test results_DE
Test protocol "Braille in DAISY Pipeline 2"
Tester: | Mischa Künzle | Software build and release notes: | v1.2.0 | https://github.com/snaekobbi/system/releases/tag/v1.2.0
Country: | Switzerland | Requirements version: | v1.2 | https://github.com/snaekobbi/requirements/releases/tag/v1.2
Date: | 2015-09-18 | CSS Specification: |  | http://snaekobbi.github.io/braille-css-spec/master/index.html
Test Case 4.3:34; Test for Uncontracted braille
Requirement ID: | 4.3.34
Description: | The system shall support the braille code used in Denmark, Finland, Norway, Sweden and Switzerland for uncontracted braille.
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | DK, NL, FI, SE, NO
Steps: | Create Job: 0. verify condition (Uncontracted) for test validity 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet **Step 4.2, set transformer query: fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) sv: (formatter:dotify)(translator:mtm) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) dk: (formatter:dotify)(translator:nota)(grade:1¦2)
Expected result: | DE | https://github.com/snaekobbi/testing/tree/master/Test%20data/Sprint_1/DE/4.3.34%2C%204.3.37%2C%204.3.41
DK
FI
NO
NO
SE
Comments:
Pass/Fail: | not yet ready
Test Case 4.3:35C; Test for possibility to leave out capital signs in some products
Requirement ID: | 4.3:35C
Description: | The system shall support the possibility to leave out capital signs in some products.
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | NL
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet: examples will be available on the requirements page (v1.2) **Step 4.2, set transformer query: nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3)
Expected result: | NL
Comments:
Pass/Fail:
Test Case 4.3:37; Test for Contracted braille
Requirement ID: | 4.3:37
Description: | The system shall support the braille code used in Denmark, Norway, Sweden and Switzerland for contracted braille.
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | DE, DK, NO
Steps: | Create Job: 0. verify condition (Contracted) for test validity 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet **Step 4.2, set transformer query: no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) dk: (formatter:dotify)(translator:nota)(grade:1¦2) de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result: | DE
DK
NO (standard text)
NO (special words that are difficult to hyphen)
Comments:
Pass/Fail: | Pass
Test Case 4.3:41; Test for Hyphenation
Requirement ID: | 4.3:41
Description: | The system shall be able to perform automatic hyphenation for uncontracted and contracted braille.
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | page width variable, word length variable, special words, default hyphenation table input. FI, DK, NO, SE, DE, NL
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet **Step 4.2, set transformer query: fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) sv: (formatter:dotify)(translator:mtm) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) dk: (formatter:dotify)(translator:nota)(grade:1¦2) de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result: | DE | https://github.com/snaekobbi/testing/tree/master/Test%20data/Sprint_1/DE/4.3.34%2C%204.3.37%2C%204.3.41
DK (grade 1)
DK (grade 2)
NO (standard text)
NO (special words that are difficult to hyphen)
SE
Comments:
Pass/Fail: | Pass
Test Case 4.4:46 / 4.4:47 / 4.4:51 / 4.4:52 / 4.4:53; Test for Horizontal and Vertical positioning and Alignment
Requirement ID: | 4.4:46, 4.4:47 (Margins, borders and padding) 4.4:51 (Indentation) 4.4:52, 4.4:53 (Text alignment)
Description: | The system shall have support for top, right, bottom and left margins on blocks. (4.4:46) The system shall have support for top, right, bottom and left borders and padding on blocks. (4.4:47) The system shall have support for first line indentation. (4.4:51) Besides left-aligned text, the system shall have support for centered and right-aligned text. (4.4.52) The system shall support block alignment relative to a vertical position on the page. (4.4:53)
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | DE, SE
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet: examples will be available on the requirements page (v1.2) **Step 4.2, set transformer query: sv: (formatter:dotify)(translator:mtm) de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result: | DE | https://github.com/snaekobbi/testing/blob/master/Test%20data/Sprint_2/DE/4.4.46%2C%204.4.47%2C%204.4.51%2C%204.4.52%2C%204.4.53/test_dtb.pef
SE
Comments:
Pass/Fail: | Pass
Test Case 4.4:54; Test for Default Whitespace handling
Requirement ID: | 4.4:54 (Default Whitespace handling)
Description: | The system shall by default handle whitespace characters (spaces, tabs, line feeds) in the source XML according to the following rules: - Comments are removed entirely and do not affect whitespace handling. - All whitespace surrounding block elements is removed. - Leading and trailing whitespace inside block elements are removed. - Sequences of whitespace characters are reduced to a single space character. Newline characters are handled as other whitespace. (4.4:54)
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | NL, NO
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet: examples will be available on the requirements page (v1.2) **Step 4.2, set transformer query: nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3)
Expected result: | NO
NL
Comments:
Pass/Fail:
Test Case 4.4:55; Test for Override of default Whitespace handling
Requirement ID: | 4.4:55 (Override of default Whitespace handling)
Description: | The user shall be able to override the default handling of whitespace for certain elements: - Prevent collapsing of sequences of whitespace. - Preserve leading and trailing whitespace inside block elements. - Preserve newline characters as forced line breaks. (4.5:55)
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | DE, DK, NO
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet: examples will be available on the requirements page (v1.2). **Step 4.2, set transformer query: no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) dk: (formatter:dotify)(translator:nota)(grade:1¦2) de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result: | NO
| DE | https://github.com/snaekobbi/testing/blob/master/Test%20data/Sprint_2/DE/4.4.55/test_preserve_whitespace.pef
DK
Comments:
Pass/Fail: | not yet ready
Test Case 4.4:74 / 4.4:75; Test for Single/Double Linespace handling and Printing
Requirement ID: | 4.4:74, 4.4:75 (Linespace handling and Printing)
Description: | The system shall support single and double line spacing. (4.4:74) When printing double-sided with line-spacing greater than 1, printed lines shall alternate on odd and even pages. (4.4:75)
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | DE, DK, FI
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet **Step 4.2, set transformer query: fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) sv: (formatter:dotify)(translator:mtm) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) dk: (formatter:dotify)(translator:nota)(grade:1¦2) de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result: | DE
DK
FI
Comments:
Pass/Fail: | not yet ready

## Sprint_3 Test results_DK
Test protocol "Braille in DAISY Pipeline 2"
Tester: | Steffen Skaarup | Software build and release notes: | v1.2.0 | https://github.com/snaekobbi/system/releases/tag/v1.2.0
Country: | Denmark | Requirements version: | v1.2 | https://github.com/snaekobbi/requirements/releases/tag/v1.2
Date: | 2015-09-16 | CSS Specification: |  | http://snaekobbi.github.io/braille-css-spec/master/index.html
Test Case 4.3:34; Test for Uncontracted braille
Requirement ID: | 4.3.34
Description: | The system shall support the braille code used in Denmark, Finland, Norway, Sweden and Switzerland for uncontracted braille.
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | DK, NL, FI, SE, NO
Steps: | Create Job: 0. verify condition (Uncontracted) for test validity 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet **Step 4.2, set transformer query: fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) sv: (formatter:dotify)(translator:mtm) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) dk: (formatter:dotify)(translator:nota)(grade:1¦2)
Expected result: | DE
| DK | https://github.com/stesk/danishbraille/blob/master/tests/translation/text_sample_grade1.pef
FI
NO
NO
SE
Comments:
Pass/Fail:
Test Case 4.3:35C; Test for possibility to leave out capital signs in some products
Requirement ID: | 4.3:35C
Description: | The system shall support the possibility to leave out capital signs in some products.
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | NL
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet: examples will be available on the requirements page (v1.2) **Step 4.2, set transformer query: nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3)
Expected result: | NL
Comments:
Pass/Fail:
Test Case 4.3:37; Test for Contracted braille
Requirement ID: | 4.3:37
Description: | The system shall support the braille code used in Denmark, Norway, Sweden and Switzerland for contracted braille.
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | DE, DK, NO
Steps: | Create Job: 0. verify condition (Contracted) for test validity 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet **Step 4.2, set transformer query: no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) dk: (formatter:dotify)(translator:nota)(grade:1¦2) de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result: | DE
| DK | https://github.com/stesk/danishbraille/blob/master/tests/translation/text_sample_grade2.pef
NO (standard text)
NO (special words that are difficult to hyphen)
Comments:
Pass/Fail:
Test Case 4.3:41; Test for Hyphenation
Requirement ID: | 4.3:41
Description: | The system shall be able to perform automatic hyphenation for uncontracted and contracted braille.
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | page width variable, word length variable, special words, default hyphenation table input. FI, DK, NO, SE, DE, NL
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet **Step 4.2, set transformer query: fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) sv: (formatter:dotify)(translator:mtm) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) dk: (formatter:dotify)(translator:nota)(grade:1¦2) de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result: | DE
| DK (grade 1) | https://github.com/stesk/danishbraille/blob/master/tests/formatting/hyphenation_sample_grade1.pef
| DK (grade 2) | https://github.com/stesk/danishbraille/blob/master/tests/formatting/hyphenation_sample_grade2.pef
NO (standard text)
NO (special words that are difficult to hyphen)
SE
Comments:
Pass/Fail:
Test Case 4.4:46 / 4.4:47 / 4.4:51 / 4.4:52 / 4.4:53; Test for Horizontal and Vertical positioning and Alignment
Requirement ID: | 4.4:46, 4.4:47 (Margins, borders and padding) 4.4:51 (Indentation) 4.4:52, 4.4:53 (Text alignment)
Description: | The system shall have support for top, right, bottom and left margins on blocks. (4.4:46) The system shall have support for top, right, bottom and left borders and padding on blocks. (4.4:47) The system shall have support for first line indentation. (4.4:51) Besides left-aligned text, the system shall have support for centered and right-aligned text. (4.4.52) The system shall support block alignment relative to a vertical position on the page. (4.4:53)
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | DE, SE
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet: examples will be available on the requirements page (v1.2) **Step 4.2, set transformer query: sv: (formatter:dotify)(translator:mtm) de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result: | DE
SE
Comments:
Pass/Fail:
Test Case 4.4:54; Test for Default Whitespace handling
Requirement ID: | 4.4:54 (Default Whitespace handling)
Description: | The system shall by default handle whitespace characters (spaces, tabs, line feeds) in the source XML according to the following rules: - Comments are removed entirely and do not affect whitespace handling. - All whitespace surrounding block elements is removed. - Leading and trailing whitespace inside block elements are removed. - Sequences of whitespace characters are reduced to a single space character. Newline characters are handled as other whitespace. (4.4:54)
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | NL, NO
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet: examples will be available on the requirements page (v1.2) **Step 4.2, set transformer query: nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3)
Expected result: | NO
NL
Comments:
Pass/Fail:
Test Case 4.4:55; Test for Override of default Whitespace handling
Requirement ID: | 4.4:55 (Override of default Whitespace handling)
Description: | The user shall be able to override the default handling of whitespace for certain elements: - Prevent collapsing of sequences of whitespace. - Preserve leading and trailing whitespace inside block elements. - Preserve newline characters as forced line breaks. (4.5:55)
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | DE, DK, NO
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet: examples will be available on the requirements page (v1.2). **Step 4.2, set transformer query: no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) dk: (formatter:dotify)(translator:nota)(grade:1¦2) de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result: | NO
DE
| DK | https://github.com/stesk/danishbraille/blob/master/tests/formatting/override_whitespace.pef
Comments: | Bug fixed; final newline no longer ignored.
Pass/Fail: | PASS
Test Case 4.4:74 / 4.4:75; Test for Single/Double Linespace handling and Printing
Requirement ID: | 4.4:74, 4.4:75 (Linespace handling and Printing)
Description: | The system shall support single and double line spacing. (4.4:74) When printing double-sided with line-spacing greater than 1, printed lines shall alternate on odd and even pages. (4.4:75)
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | DE, DK, FI
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet **Step 4.2, set transformer query: fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) sv: (formatter:dotify)(translator:mtm) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) dk: (formatter:dotify)(translator:nota)(grade:1¦2) de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result: | DE
DK
FI
Comments:
Pass/Fail:

## Sprint_3 Test results_NL
Test protocol "Braille in DAISY Pipeline 2"
Tester: | Davy Kager | Software build and release notes: | v1.2.0 | https://github.com/snaekobbi/system/releases/tag/v1.2.0
Country: | Netherlands | Requirements version: | v1.2 | https://github.com/snaekobbi/requirements/releases/tag/v1.2
Date: | 2015-09-17 | CSS Specification: |  | http://snaekobbi.github.io/braille-css-spec/master/index.html
Test Case 4.3:34; Test for Uncontracted braille
Requirement ID: | 4.3.34
Description: | The system shall support the braille code used in Denmark, Finland, Norway, Sweden and Switzerland for uncontracted braille.
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | DK, NL, FI, SE, NO
Steps: | Create Job: 0. verify condition (Uncontracted) for test validity 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet **Step 4.2, set transformer query: fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) sv: (formatter:dotify)(translator:mtm) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) dk: (formatter:dotify)(translator:nota)(grade:1¦2)
Expected result: | DE
DK
FI
NO
NO
SE
Comments: | Translation is good, but this system test revealed a higher-level issue. | https://github.com/snaekobbi/pipeline-mod-dedicon/issues/2
Pass/Fail: | Pass
Test Case 4.3:35C; Test for possibility to leave out capital signs in some products
Requirement ID: | 4.3:35C
Description: | The system shall support the possibility to leave out capital signs in some products.
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | NL | https://github.com/snaekobbi/testing/pull/4
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet: examples will be available on the requirements page (v1.2) **Step 4.2, set transformer query: nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3)
Expected result: | NL | https://raw.githubusercontent.com/snaekobbi/testing/master/Test%20data/Sprint_3/NL/4.3.35C/289409_Boos%20boos%20boos%204_3_35C.pef
Comments:
Pass/Fail: | Pass
Test Case 4.3:37; Test for Contracted braille
Requirement ID: | 4.3:37
Description: | The system shall support the braille code used in Denmark, Norway, Sweden and Switzerland for contracted braille.
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | DE, DK, NO
Steps: | Create Job: 0. verify condition (Contracted) for test validity 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet **Step 4.2, set transformer query: no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) dk: (formatter:dotify)(translator:nota)(grade:1¦2) de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result: | DE
DK
NO (standard text)
NO (special words that are difficult to hyphen)
Comments:
Pass/Fail:
Test Case 4.3:41; Test for Hyphenation
Requirement ID: | 4.3:41
Description: | The system shall be able to perform automatic hyphenation for uncontracted and contracted braille.
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | page width variable, word length variable, special words, default hyphenation table input. FI, DK, NO, SE, DE, NL
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet **Step 4.2, set transformer query: fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) sv: (formatter:dotify)(translator:mtm) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) dk: (formatter:dotify)(translator:nota)(grade:1¦2) de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result: | DE
DK (grade 1)
DK (grade 2)
NO (standard text)
NO (special words that are difficult to hyphen)
SE
Comments:
Pass/Fail:
Test Case 4.4:46 / 4.4:47 / 4.4:51 / 4.4:52 / 4.4:53; Test for Horizontal and Vertical positioning and Alignment
Requirement ID: | 4.4:46, 4.4:47 (Margins, borders and padding) 4.4:51 (Indentation) 4.4:52, 4.4:53 (Text alignment)
Description: | The system shall have support for top, right, bottom and left margins on blocks. (4.4:46) The system shall have support for top, right, bottom and left borders and padding on blocks. (4.4:47) The system shall have support for first line indentation. (4.4:51) Besides left-aligned text, the system shall have support for centered and right-aligned text. (4.4.52) The system shall support block alignment relative to a vertical position on the page. (4.4:53)
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | DE, SE
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet: examples will be available on the requirements page (v1.2) **Step 4.2, set transformer query: sv: (formatter:dotify)(translator:mtm) de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result: | DE
SE
Comments:
Pass/Fail:
Test Case 4.4:54; Test for Default Whitespace handling
Requirement ID: | 4.4:54 (Default Whitespace handling)
Description: | The system shall by default handle whitespace characters (spaces, tabs, line feeds) in the source XML according to the following rules: - Comments are removed entirely and do not affect whitespace handling. - All whitespace surrounding block elements is removed. - Leading and trailing whitespace inside block elements are removed. - Sequences of whitespace characters are reduced to a single space character. Newline characters are handled as other whitespace. (4.4:54)
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | NL, NO
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet: examples will be available on the requirements page (v1.2) **Step 4.2, set transformer query: nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3)
Expected result: | NO
| NL | https://raw.githubusercontent.com/snaekobbi/testing/master/Test%20data/Sprint_3/NL/4.4.54/295593_Whitespace%204_4_54.pef
Comments: | Added for sprint #3. | https://github.com/snaekobbi/testing/commit/6f5b9f958f0e844ecff2f373bb83c33062a3803f
Pass/Fail: | Pass
Test Case 4.4:55; Test for Override of default Whitespace handling
Requirement ID: | 4.4:55 (Override of default Whitespace handling)
Description: | The user shall be able to override the default handling of whitespace for certain elements: - Prevent collapsing of sequences of whitespace. - Preserve leading and trailing whitespace inside block elements. - Preserve newline characters as forced line breaks. (4.5:55)
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | DE, DK, NO
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet: examples will be available on the requirements page (v1.2). **Step 4.2, set transformer query: no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) dk: (formatter:dotify)(translator:nota)(grade:1¦2) de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result: | NO
DE
DK
Comments:
Pass/Fail:
Test Case 4.4:74 / 4.4:75; Test for Single/Double Linespace handling and Printing
Requirement ID: | 4.4:74, 4.4:75 (Linespace handling and Printing)
Description: | The system shall support single and double line spacing. (4.4:74) When printing double-sided with line-spacing greater than 1, printed lines shall alternate on odd and even pages. (4.4:75)
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | DE, DK, FI
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet **Step 4.2, set transformer query: fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) sv: (formatter:dotify)(translator:mtm) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) dk: (formatter:dotify)(translator:nota)(grade:1¦2) de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result: | DE
DK
FI
Comments:
Pass/Fail:

## Sprint_3 Test results_NO
Test protocol "Braille in DAISY Pipeline 2"
Tester: | Kari Rudjord | Software build and release notes: | v1.2.0 | https://github.com/snaekobbi/system/releases/tag/v1.2.0
Country: | Norway | Requirements version: | v1.2 | https://github.com/snaekobbi/requirements/releases/tag/v1.2
Date: | 2015-09-23 | CSS Specification: |  | http://snaekobbi.github.io/braille-css-spec/master/index.html
Test Case 4.3:34; Test for Uncontracted braille
Requirement ID: | 4.3.34
Description: | The system shall support the braille code used in Denmark, Finland, Norway, Sweden and Switzerland for uncontracted braille.
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | DK, NL, FI, SE, NO
Steps: | Create Job: 0. verify condition (Uncontracted) for test validity 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet **Step 4.2, set transformer query: fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) sv: (formatter:dotify)(translator:mtm) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) dk: (formatter:dotify)(translator:nota)(grade:1¦2)
Expected result: | DE
DK
FI
| NO | https://raw.githubusercontent.com/snaekobbi/testing/master/Test%20data/Sprint_3/NO/Test.PEF.4.3.34.Norwegian%20uncontracted%20braille.2.pef
SE
Comments: | Almost everything in place now. Remains to test two things that Bert is working on+B7: rules for e-mailadress and emphasis (to separate bild and italic when they appear together)
Pass/Fail: | Pass
Test Case 4.3:35C; Test for possibility to leave out capital signs in some products
Requirement ID: | 4.3:35C
Description: | The system shall support the possibility to leave out capital signs in some products.
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | NL
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet: examples will be available on the requirements page (v1.2) **Step 4.2, set transformer query: nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3)
Expected result: | NL
Comments:
Pass/Fail:
Test Case 4.3:37; Test for Contracted braille
Requirement ID: | 4.3:37
Description: | The system shall support the braille code used in Denmark, Norway, Sweden and Switzerland for contracted braille.
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | DE, DK, NO
Steps: | Create Job: 0. verify condition (Contracted) for test validity 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet **Step 4.2, set transformer query: no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) dk: (formatter:dotify)(translator:nota)(grade:1¦2) de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result: | DE
DK
| NO (grade1) | https://raw.githubusercontent.com/snaekobbi/testing/master/Test%20data/Sprint_3/NO/Test.PEF.4.3.37.Contractedbrailletest.grade1.pef
| NO (grade2) | https://raw.githubusercontent.com/snaekobbi/testing/master/Test%20data/Sprint_3/NO/Test.PEF.4.3.37.Contractedbrailletest.grade2.pef
Comments: | Grade 1 and 2 correct, just a few minor errors that Ammar will correct. My proofreader made no comments on hyphenation i contracted braille.
Pass/Fail: | Pass
Test Case 4.3:41; Test for Hyphenation
Requirement ID: | 4.3:41
Description: | The system shall be able to perform automatic hyphenation for uncontracted and contracted braille.
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | page width variable, word length variable, special words, default hyphenation table input. FI, DK, NO, SE, DE, NL
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet **Step 4.2, set transformer query: fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) sv: (formatter:dotify)(translator:mtm) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) dk: (formatter:dotify)(translator:nota)(grade:1¦2) de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result: | DE
DK (grade 1)
DK (grade 2)
| NO (standard text) | https://github.com/snaekobbi/testing/blob/master/Test%20data/Sprint_1/NO/4.3.34%2C%204.3.41/Test.PEF.Norwegian%20hyphenation.pef
| NO (special words that are difficult to hyphen) | https://github.com/snaekobbi/testing/blob/master/Test%20data/Sprint_1/NO/4.3.34%2C%204.3.41/Test.PEF.4.3.41.Hyphenation.Uncontracted%20braille.pef
SE
Comments: | The hyphenation works, but I want it to hyphenate more. I think Bert/Ammar is working on a solution.
Pass/Fail: | To be improved
Test Case 4.4:46 / 4.4:47 / 4.4:51 / 4.4:52 / 4.4:53; Test for Horizontal and Vertical positioning and Alignment
Requirement ID: | 4.4:46, 4.4:47 (Margins, borders and padding) 4.4:51 (Indentation) 4.4:52, 4.4:53 (Text alignment)
Description: | The system shall have support for top, right, bottom and left margins on blocks. (4.4:46) The system shall have support for top, right, bottom and left borders and padding on blocks. (4.4:47) The system shall have support for first line indentation. (4.4:51) Besides left-aligned text, the system shall have support for centered and right-aligned text. (4.4.52) The system shall support block alignment relative to a vertical position on the page. (4.4:53)
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | DE, SE
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet: examples will be available on the requirements page (v1.2) **Step 4.2, set transformer query: sv: (formatter:dotify)(translator:mtm) de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result: | DE
SE
Comments:
Pass/Fail:
Test Case 4.4:54; Test for Default Whitespace handling
Requirement ID: | 4.4:54 (Default Whitespace handling)
Description: | The system shall by default handle whitespace characters (spaces, tabs, line feeds) in the source XML according to the following rules: - Comments are removed entirely and do not affect whitespace handling. - All whitespace surrounding block elements is removed. - Leading and trailing whitespace inside block elements are removed. - Sequences of whitespace characters are reduced to a single space character. Newline characters are handled as other whitespace. (4.4:54)
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | NL, NO
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet: examples will be available on the requirements page (v1.2) **Step 4.2, set transformer query: nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3)
Expected result: | NO | https://raw.githubusercontent.com/snaekobbi/testing/master/Test%20data/Sprint_3/NO/Test.PEF.4.4.54.whitespace.pef
NL
Comments:
Pass/Fail: | Pass
Test Case 4.4:55; Test for Override of default Whitespace handling
Requirement ID: | 4.4:55 (Override of default Whitespace handling)
Description: | The user shall be able to override the default handling of whitespace for certain elements: - Prevent collapsing of sequences of whitespace. - Preserve leading and trailing whitespace inside block elements. - Preserve newline characters as forced line breaks. (4.5:55)
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | DE, DK, NO
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet: examples will be available on the requirements page (v1.2). **Step 4.2, set transformer query: no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) dk: (formatter:dotify)(translator:nota)(grade:1¦2) de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result: | NO | https://raw.githubusercontent.com/snaekobbi/testing/master/Test%20data/Sprint_3/NO/Test.PEF.4.4.55.whitespace.pef
DE
DK
Comments:
Pass/Fail: | Pass
Test Case 4.4:74 / 4.4:75; Test for Single/Double Linespace handling and Printing
Requirement ID: | 4.4:74, 4.4:75 (Linespace handling and Printing)
Description: | The system shall support single and double line spacing. (4.4:74) When printing double-sided with line-spacing greater than 1, printed lines shall alternate on odd and even pages. (4.4:75)
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | DE, DK, FI
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet **Step 4.2, set transformer query: fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) sv: (formatter:dotify)(translator:mtm) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) dk: (formatter:dotify)(translator:nota)(grade:1¦2) de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result: | DE
DK
FI
Comments:
Pass/Fail:

## Sprint_3 Test results_SE
Test protocol "Braille in DAISY Pipeline 2"
Tester: | Jens Chreisti | Software build and release notes: | v1.2.0 | https://github.com/snaekobbi/system/releases/tag/v1.2.0
Country: | Sweden | Requirements version: | v1.2 | https://github.com/snaekobbi/requirements/releases/tag/v1.2
Date: | 2015-09-17 | CSS Specification: |  | http://snaekobbi.github.io/braille-css-spec/master/index.html
Test Case 4.3:34; Test for Uncontracted braille
Requirement ID: | 4.3.34
Description: | The system shall support the braille code used in Denmark, Finland, Norway, Sweden and Switzerland for uncontracted braille.
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | DK, NL, FI, SE, NO
Steps: | Create Job: 0. verify condition (Uncontracted) for test validity 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet **Step 4.2, set transformer query: fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) sv: (formatter:dotify)(translator:mtm) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) dk: (formatter:dotify)(translator:nota)(grade:1¦2)
Expected result: | DE
DK
FI
NO
NO
| SE | https://github.com/snaekobbi/testing/blob/master/Test%20data/Sprint_1/SE/4.3.34%2C%204.3.41/P20151.pef
Comments:
Pass/Fail:
Test Case 4.3:35C; Test for possibility to leave out capital signs in some products
Requirement ID: | 4.3:35C
Description: | The system shall support the possibility to leave out capital signs in some products.
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | NL
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet: examples will be available on the requirements page (v1.2) **Step 4.2, set transformer query: nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3)
Expected result: | NL
Comments:
Pass/Fail:
Test Case 4.3:37; Test for Contracted braille
Requirement ID: | 4.3:37
Description: | The system shall support the braille code used in Denmark, Norway, Sweden and Switzerland for contracted braille.
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | DE, DK, NO
Steps: | Create Job: 0. verify condition (Contracted) for test validity 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet **Step 4.2, set transformer query: no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) dk: (formatter:dotify)(translator:nota)(grade:1¦2) de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result: | DE
DK
Comments:
Pass/Fail:
Test Case 4.3:41; Test for Hyphenation
Requirement ID: | 4.3:41
Description: | The system shall be able to perform automatic hyphenation for uncontracted and contracted braille.
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | page width variable, word length variable, special words, default hyphenation table input. FI, DK, NO, SE, DE, NL
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet **Step 4.2, set transformer query: fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) sv: (formatter:dotify)(translator:mtm) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) dk: (formatter:dotify)(translator:nota)(grade:1¦2) de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result: | DE
DK (grade 1)
DK (grade 2)
NO (standard text)
NO (special words that are difficult to hyphen)
| SE | https://github.com/snaekobbi/testing/blob/master/Test%20data/Sprint_1/SE/4.3.34%2C%204.3.41/P20151.pef
Comments:
Pass/Fail:
Test Case 4.4:46 / 4.4:47 / 4.4:51 / 4.4:52 / 4.4:53; Test for Horizontal and Vertical positioning and Alignment
Requirement ID: | 4.4:46, 4.4:47 (Margins, borders and padding) 4.4:51 (Indentation) 4.4:52, 4.4:53 (Text alignment)
Description: | The system shall have support for top, right, bottom and left margins on blocks. (4.4:46) The system shall have support for top, right, bottom and left borders and padding on blocks. (4.4:47) The system shall have support for first line indentation. (4.4:51) Besides left-aligned text, the system shall have support for centered and right-aligned text. (4.4.52) The system shall support block alignment relative to a vertical position on the page. (4.4:53)
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | DE, SE
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet: examples will be available on the requirements page (v1.2) **Step 4.2, set transformer query: sv: (formatter:dotify)(translator:mtm) de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result: | DE
| SE | https://github.com/snaekobbi/testing/blob/master/Test%20data/Sprint_2/SE/4.3.34%2C%204.3.41%2C%204.4.46%2C%204.4.47%2C%204.4.51/P20151.pef
Comments: | 4.4.46: Extra preceeding empty line for all paragraphs 4.4.47: Borders are OK, but extra preceeding empty line for all paragraphs.
Pass/Fail: | 4.4.46: fail. 4.4.47: fail. 4.4.52: pass. 4.4.53: pass.
Test Case 4.4:54; Test for Default Whitespace handling
Requirement ID: | 4.4:54 (Default Whitespace handling)
Description: | The system shall by default handle whitespace characters (spaces, tabs, line feeds) in the source XML according to the following rules: - Comments are removed entirely and do not affect whitespace handling. - All whitespace surrounding block elements is removed. - Leading and trailing whitespace inside block elements are removed. - Sequences of whitespace characters are reduced to a single space character. Newline characters are handled as other whitespace. (4.4:54)
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | NL, NO
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet: examples will be available on the requirements page (v1.2) **Step 4.2, set transformer query: nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3)
Expected result: | NO
NL
Comments:
Pass/Fail:
Test Case 4.4:55; Test for Override of default Whitespace handling
Requirement ID: | 4.4:55 (Override of default Whitespace handling)
Description: | The user shall be able to override the default handling of whitespace for certain elements: - Prevent collapsing of sequences of whitespace. - Preserve leading and trailing whitespace inside block elements. - Preserve newline characters as forced line breaks. (4.5:55)
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | DE, DK, NO
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet: examples will be available on the requirements page (v1.2). **Step 4.2, set transformer query: no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) dk: (formatter:dotify)(translator:nota)(grade:1¦2) de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result: | NO
DE
DK
Comments:
Pass/Fail:
Test Case 4.4:74 / 4.4:75; Test for Single/Double Linespace handling and Printing
Requirement ID: | 4.4:74, 4.4:75 (Linespace handling and Printing)
Description: | The system shall support single and double line spacing. (4.4:74) When printing double-sided with line-spacing greater than 1, printed lines shall alternate on odd and even pages. (4.4:75)
Pre-requisites: | Logged in to Web UI, valid country requirement
Test data: | DE, DK, FI
Steps: | Create Job: 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet* 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | *Step 4.1, set stylesheet **Step 4.2, set transformer query: fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) sv: (formatter:dotify)(translator:mtm) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) dk: (formatter:dotify)(translator:nota)(grade:1¦2) de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result: | DE
DK
FI
Comments:
Pass/Fail: