## Background and Preparation
Test protocol "Braille in DAISY Pipeline 2"
Purpose
The purpose of the test protocol and test cases are to report and verify the end-to-end system level functionality vs. the requirements. Test results are tracked through Pass/Fail verdicts against Expected result with supporting Comments and Priorities for failed test cases.
References
Requirements:
https://drive.google.com/drive/folders/0B_Q0CSMAbmEdeHFhMDBfeUJPaHM
http://dev.pef-format.org/dp2/master/index.xhtml
Software build + release notes:
https://github.com/snaekobbi/system/releases
Preconditions
Test server environment configured and ready including integrated pipeline and braille modules:
http://158.39.20.55
Test data prepared.
Agency specific stylesheets defined.
Preparations
System installation: 1. Create and Configure Administrative account for Web UI 2. Connect Web UI to the Pipeline 2 engine Web API 3. Set content / test data storage directories Tester login: 1. Visit Web UI/Test server login page 2. Enter E-mail/UserID and Password 3. Click Login 4. Click Get started
Priority Guideline
P1 (High): To be fixed in the current sprint, next iteration P2 (Medium): To be fixed in the next sprint P3 (Low): To be fixed in a future sprint

## Sprint_4 Test cases
Test protocol "Braille in DAISY Pipeline 2"
Tester: | Davy Kager | Software build and release notes: | v1.3.0 | https://github.com/snaekobbi/system/releases/tag/v1.3.0
Country: | NL | Requirements version: | v1.3 | https://github.com/snaekobbi/requirements/releases/tag/v1.3
Date: | 2015-10-29 | CSS Specification: |  | http://snaekobbi.github.io/braille-css-spec/master/index.html
Test Case 4.4:74 - 4.4:75, Test for Single/Double Linespace handling and Printing
Requirement ID: | 4.4:74, 4.4:75 (Linespace handling and Printing)
Description: | The system shall support single and double line spacing. (4.4:74) When printing double-sided with line-spacing greater than 1, printed lines shall alternate on odd and even pages. (4.4:75)
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | DE, DK, FI, SE
Steps: | Create Job: 0. verify condition (Uncontracted) for test validity 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | **4.2, set transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2) dk: (formatter:dotify)(translator:nota)(grade:1¦2) fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) sv: (formatter:dotify)(translator:mtm)
Expected result: | DE
DK
FI
SE
Comments:
Pass/Fail:
Priority: | (See Priority Guideline in Background and Preparation TAB)
Test Case 4.5:78 - 85, Support for pagination (division in pages)
Requirement ID: | 4.5:78 (Pagination) 4.5:80, 4.5:81, 4.5:82 (Page layout) 4.5:84, 4.5:85 (Single- vs Double-sided printing)
Description: | The user shall have control over page breaking by means of: ◦ inserting hard page breaks, ◦ protecting blocks from being split across multiple pages, ◦ avoiding page breaks within blocks leaving only the first line(s) on the first page (orphan control), ◦ avoiding page breaks within blocks leaving only the last line(s) on the second page (widow control), and ◦ keeping a block’s first line(s) on the same page as the preceding block. (4.5:78) The user shall have control over the page dimensions and the size of page margins. (4.5:80) There shall be support for content in the header and footer of pages. Content can be rendered in the left corner, the center and the right corner. (4.5:81) The header and footer layout shall be able to change between sections within the document. (4.5:82) When printing double-sided, there shall be support for hard page breaks that jump to the next right- or left-hand page. (4.5.84) When printing double-sided, the system shall allow the page layout (page margins as well as header and footer layout) to differ between left- and right-hand pages. (4.5:85)
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | DE, DK, FI, NL, NO, SE
Steps: | Create Job: 0. verify condition (Uncontracted) for test validity 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | **4.2, set transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2) dk: (formatter:dotify)(translator:nota)(grade:1¦2) fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) sv: (formatter:dotify)(translator:mtm)
Expected result: | DE
DK
FI
| NL | https://github.com/snaekobbi/testing/blob/ddc1fbb3595d7f445a2b9a19d5f375106ade4de9/Test%20data/Sprint_4/NL/pagination-test-1.xml
NO
SE
Comments: | Only the very basic features have been tested, i.e. margins, header text (page numbers) and automatic page breaking. At the start of the sprint there were some issues, documented as comments in NL/pagination-test-1.xml. These look to have been fixed during the course of the sprint. TODO: for next sprint, test more advanced features.
Pass/Fail: | Pass
Priority: | (See Priority Guideline in Background and Preparation TAB) | P2
Test Case 4.7:102, Support for generated content (variables, counters)
Requirement ID: | 4.7:102 (Evaluation of variables and counters)
Description: | The system shall be able to evaluate certain variables and counters at so-called "fields", for example on the title page or in the page header or footer. Supported variables shall include at least the current braille page number, the current print page number or range of print pages contained in the current braille page, the current volume number, the total number of volumes, the total number of braille pages or sheets contained in the current volume or book, the current chapter title, the current chapter number, and the date. (4.7:102) | NOTE: In this sprint we deal with at least braille page numbering and print page numbering (possibly page range) in the header/footer in various required number formats.
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | DE, DK, FI, NL, NO, SE
Steps: | Create Job: 0. verify condition (Uncontracted) for test validity 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | **4.2, set transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2) dk: (formatter:dotify)(translator:nota)(grade:1¦2) fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) sv: (formatter:dotify)(translator:mtm)
Expected result: | DE
DK
FI
NL
NO
SE
Comments: | Tested braille page number in page header.
Pass/Fail: | Pass
Priority: | (See Priority Guideline in Background and Preparation TAB) | P3
Test Case 4.8:105 - 107, Support for indication of original pagination
Requirement ID: | 4.8:105, 4.8:106, 4.8:107 (Indication of print page breaks)
Description: | The system shall provide the possibility of rendering print page breaks as full lines across the width of the page, optionally with the page number of the new print page incorporated in the line. A line break is inserted first whenever a print page break indicator is rendered, and following text continues on the line below the indicator. In other words, the print page break is not taken out of the normal flow of the text in order not to lose precision. (4.8:105) The system shall provide the possibility of rendering print page breaks as marks in the left margin, taking them out of the normal text flow so that text that follows the element can continue on the same line. (4.8:106) The system shall support skipping print page breaks when no text precedes or follows on the same braille page. (4.8:107)
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | DE, DK, FI, NL, NO, SE
Steps: | Create Job: 0. verify condition (Uncontracted) for test validity 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | **4.2, set transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2) dk: (formatter:dotify)(translator:nota)(grade:1¦2) fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) sv: (formatter:dotify)(translator:mtm)
Expected result: | DE
DK
FI
NL
NO
SE
Comments: | Not implemented in Dedicon's CSS yet. Add for next sprint?
Pass/Fail:
Priority: | (See Priority Guideline in Background and Preparation TAB) | P2
Test Case 4.9:110 - 113, Support for ordering and monitoring of braille production (templating, job management)
Requirement ID: | 4.9:110 (Reuse templates) 4.9:111 (Create templates) 4.9:112 (Save jobs) 4.9:113 (Monitor jobs)
Description: | Users shall be able to reuse templates. (4.9:110) Certain users shall be able to create templates (4.9:111) The system shall save jobs so that e.g. a job history can be showed, and jobs can be rerun. (4.9:112) The user shall be able to monitor jobs: get an overview of the jobs waiting, running, finished, etc., and receive notifications of certain events. (4.9:113)
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | DE, DK, FI, NL, NO, SE
Steps: | Create Job: 0. verify condition (Uncontracted) for test validity 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | **4.2, set transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2) dk: (formatter:dotify)(translator:nota)(grade:1¦2) fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) sv: (formatter:dotify)(translator:mtm)
Expected result: | DE
DK
FI
NL
NO
SE
Comments: | Tested Restart job and Delete job with arbitrary file.
Pass/Fail: | Pass
Priority: | (See Priority Guideline in Background and Preparation TAB)
Test Case 4.7:94 - 103, Support for generated content (numbering, number formatting, cross-references)
Requirement ID: | 4.7:94 (Number formatting) 4.7:97 (Automatic numbering) 4.7:99 (Resetting numbering) 4.7:103 (Evaluation of variables and counters)
Description: | The system shall support formatting of numbers and other variables in a wide selection of formats. Supported formats shall include at least arabic, roman (small and capital), alpha (small and capital), downshifted, written out, and various date formats. It shall be possible to specify number prefixes and suffixes too. Some numbers might need specialized translation, such as ranges of print pages. (4.7:94) The system shall be able to perform automatic numbering of braille pages and volumes. (4.7:97) The system shall support resetting of braille page numbering at the start of major sections (frontmatter, bodymatter, rearmatter). Resetting numbering for each volume is not part of this requirement. (4.7:99) The system shall support insertion of certain variables and counters at references evaluated at the target. An example is references in a table of contents. Supported variables shall include the print page number at the target, the braille page number at the target, and the note number if the target is a renumbered note. This feature relies on explicit markup of references. (4.7:103)
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | DE, DK, FI, NL, NO, SE
Steps: | Create Job: 0. verify condition (Uncontracted) for test validity 1. upload files to process 2. select Script to run 3. select Source file 4. set Optional parameters 4.1 set stylesheet 4.2 set transformer query** 5. click Start job 6. see storage Result directory file 7.verify output result | **4.2, set transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2) dk: (formatter:dotify)(translator:nota)(grade:1¦2) fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) sv: (formatter:dotify)(translator:mtm)
Expected result: | DE
DK
FI
NL
NO
SE
Comments: | Tested 4.7:97, others need more specification at Dedicon plus implementation and testing in future sprint.
Pass/Fail: | Pass
Priority: | (See Priority Guideline in Background and Preparation TAB) | P3