## Background and Preparation
Test protocol "Braille in DAISY Pipeline 2"
Purpose
The purpose of the test protocol and test cases are to report and verify the end-to-end system level functionality vs. the requirements. Test results are tracked through Pass/Fail verdicts against Expected result with supporting Comments and Priorities for failed test cases.
References
Requirements:
https://drive.google.com/drive/folders/0B_Q0CSMAbmEdeHFhMDBfeUJPaHM
http://dev.pef-format.org/dp2/master/index.xhtml
Software build + release notes:
https://github.com/snaekobbi/system/releases
Preconditions
Test server environment configured and ready including integrated pipeline and braille modules:
http://158.39.20.55
Test data prepared.
Agency specific stylesheets defined.
Preparations
System installation: 1. Create and Configure Administrative account for Web UI 2. Connect Web UI to the Pipeline 2 engine Web API 3. Set content / test data storage directories Tester login: 1. Visit Web UI/Test server login page 2. Enter E-mail/UserID and Password 3. Click Login 4. Click Get started

## Sprint_10 Test cases_DE
Test protocol "Braille in DAISY Pipeline 2"
Tester: | Mischa Künzle | Software build and release notes: | v1.6.0 | https://github.com/snaekobbi/system/releases/tag/v1.6.0
Country: | Switzerland | Requirements version: | v1.5 | https://github.com/snaekobbi/requirements/releases/tag/v1.5
Date: | 2016-06-09 | CSS Specification: |  | http://snaekobbi.github.io/braille-css-spec/master/index.html
|  | Template User Guide: |  | https://github.com/daisy/pipeline-webui/wiki/Templating
Test Case 3.4:8, Support for EPUB3 as Input
Requirement ID: | 3.4:8
Description: | The system shall support EPUB 3 (conforming to the MTM procurement specification) as input. (3.4:8) | epub3-to-pef
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DE, DK, FI, NL, NO, SV
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2) dk: (formatter:dotify)(translator:nota)(grade:1¦2) fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) sv: (formatter:dotify)(translator:mtm)
Expected result:
Comments:
Pass/Fail: | Pass
Feature Priority: | 1
Test Case 3.5:15, Support for Plain text output
Requirement ID: | 3.5:15
Description: | The system shall be able to output plain text using a user-specified braille table and form feed character. (3.5:15)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DE, DK, FI, NL, NO, SV
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2) dk: (formatter:dotify)(translator:nota)(grade:1¦2) fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) sv: (formatter:dotify)(translator:mtm)
Expected result:
Comments: | part of character mapping not correct
Pass/Fail: | Fail
Feature Priority: | 1
Test Case 4.3:36, Support for Double letter spacing
Requirement ID: | 4.3:36 | http://snaekobbi.github.io/requirements/v1.5/#4.3:36
Description: | The system shall support double letter spacing, meaning adding a space between characters. Some characters should be kept together such as a capital sign and a letter. (4.3:36) | Example: https://github.com/snaekobbi/pipeline-mod-celia/blob/6a3a50e586e31b12947fba6406baa3dcb9ac548f/src/test/xprocspec/test_css_formatter.xprocspec
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | FI
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: fi: (formatter:dotify)(translator:celia) CSS Specification details: http://snaekobbi.github.io/braille-css-spec/#word-spacing-the-word-spacing-property http://snaekobbi.github.io/braille-css-spec/#h3_letter-spacing-the-letter-spacing-property
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 2
Test Case 4.3:37, Support for Contracted bralle
Requirement ID: | 4.3:37 | http://snaekobbi.github.io/requirements/v1.5/#4.3:37
Description: | The system shall support the braille code used in Denmark, Norway, Sweden and Switzerland for contracted braille. (4.3:37)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DK
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: dk: (formatter:dotify)(translator:nota)(grade:1¦2)
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 1
Test Case 4.3:38, Support for Marking of text-level semantics with braille indicators
Requirement ID: | 4.3:38 | http://snaekobbi.github.io/requirements/v1.5/#4.3:38
Description: | The system shall support marking of text-level semantics (i.e. em, strong) with braille indicators.
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DE, FI, NL, NO
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2) fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3)
Expected result:
Comments: | not ready for test accordting to huboard
Pass/Fail:
Feature Priority: | 1
Test Case 4.3:42, Support for non-standard hyphenation
Requirement ID: | 4.3:42 | http://snaekobbi.github.io/requirements/v1.5/#4.3:42
Description: | The system shall support non-standard hyphenation. By non-standard hyphenation we mean that the spelling of a word can change when it is hyphenated. The braille translation of a hyphenated word can only change because the spelling changes, not e.g. because it is contracted in some other way. In other words the definition of non-standard hyphenation is not “extrapolated to braille”. (4.3:42)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | NO
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3)
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 1
Test Case 4.4:48, Support for Collapsing margins
Requirement ID: | 4.4:48 | http://snaekobbi.github.io/requirements/v1.5/#4.4:48
Description: | By default margins shall be collapsing. However there shall be a way to override this behaviour. (4.4:48)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DE
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result:
Comments:
Pass/Fail: | Pass
Feature Priority: | 2
Test Case 4.4:49, Support for Empty lines at top and bottom of page
Requirement ID: | 4.4:49 | http://snaekobbi.github.io/requirements/v1.5/#4.4:49
Description: | By default empty lines at the top and bottom of a page shall be suppressed. However there shall be a way to override this behaviour. (4.4:49)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DE
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result:
Comments:
Pass/Fail: | Pass
Feature Priority: | 2
Test Case 4.4:50, Support for Shrinking a block with a border to the size of its content
Requirement ID: | 4.4:50 | http://snaekobbi.github.io/requirements/v1.5/#4.4:50
Description: | There shall be the possibility of shrinking a block with a border to the size of its contents. This feature shall be supported at least for blocks with left-aligned text and no nested blocks. (4.4:50)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DE
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result:
Comments: | When the heading wraps to the next line, the underlining might be one cell too long. This behavior is undesired but not disturbing. It should be corrected in the medium or long term (low priority).
Pass/Fail: | Pass, see comment
Feature Priority: | 2
Test Case 4.4:74, Support for single and double line spacing
Requirement ID: | 4.4:74 | http://snaekobbi.github.io/requirements/v1.5/#4.4:74
Description: | It shall be possible to configure line spacing on section level, i.e. to switch from a single line spacing section to a double line spacing section or vice-versa. (4.4:74)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | NO
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3)
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 1
Test Case 4.5:82, Support for header and footer layout change between sections
Requirement ID: | 4.5:82 | http://snaekobbi.github.io/requirements/v1.5/#4.5:82
Description: | The header and footer layout shall be able to change between sections within the document. (4.5:82)
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | DE
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result:
Comments: | addtitionally, braille page numbers need to be resetable and roman in the toc
Pass/Fail: | Pass, see comment
Feature Priority: | 1
Test Case 4.6:88, Support for Automatic volume breaking with constraints
Requirement ID: | 4.6:88 | http://snaekobbi.github.io/requirements/v1.5/#4.6:88
Description: | The system shall be able to perform automatic volume breaking with constraints. It shall be possible to precisely tweak the algorithm. It shall take values for minimal and maximal number of pages per volume. It shall support special ranges for the first and last volume of sections. The algorithm shall take into account that certain points in the book are better suited for being the start of a new volume than other points and that certain sections belong in certain volumes. (4.6:88)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DK, NO
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. set Optional parameters 5. click "Start job" 6. see storage Result/Output Directory file 7.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. set Optional parameters 5. click Start job 6. see storage Result/Output Directory file 7. verify output result | Transformer query: no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3)
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 1
Test Case 4.6:93, Support for Manual user control over volume breaking
Requirement ID: | 4.6:93 | http://snaekobbi.github.io/requirements/v1.5/#4.6:93
Description: | The user shall have some form of manual control over volume breaking. (4.6:93)
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | DE
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result:
Comments: | not ready for test according to huboard
Pass/Fail:
Feature Priority: | 3
Test Case 4.7:96, Support for Automatic insertion of content that is not present in the source
Requirement ID: | 4.7:96 | http://snaekobbi.github.io/requirements/v1.5/#4.7:96
Description: | The system shall support automatic insertion of content that is not present in the source. Examples include: ◦ boilerplate text inserted e.g. on the title page, ◦ metadata and details about the production process, ◦ automatic transcriber notes that give information about omitted or moved content, about how tables are rendered, ◦ etc. (4.7:96)
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | DE, DK, FI, NL, NO, SV
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2) dk: (formatter:dotify)(translator:nota)(grade:1¦2) fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) sv: (formatter:dotify)(translator:mtm)
Expected result:
Comments:
Pass/Fail: | Pass
Feature Priority: | 1
Test Case 4.7:102, Support for Evaluating certain variables and counters at so-called "fields"
Requirement ID: | 4.7:102 | http://snaekobbi.github.io/requirements/v1.5/#4.7:102
Description: | The system shall be able to evaluate certain variables and counters at so-called "fields", for example on the title page or in the page header or footer. Supported variables shall include at least the current braille page number, the current print page number or range of print pages contained in the current braille page, the current volume number, the total number of volumes, the total number of braille pages or sheets contained in the current volume or book, the current chapter title, the current chapter number, and the date. (4.7:102)
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | DE, NO
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2) dk: (formatter:dotify)(translator:nota)(grade:1¦2) fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) sv: (formatter:dotify)(translator:mtm)
Expected result:
Comments: | not ready for test according to huboard
Pass/Fail:
Feature Priority: | 1

## Sprint_10 Test cases_NL
Test protocol "Braille in DAISY Pipeline 2"
Tester: | Davy Kager | Software build and release notes: | v1.6.0 | https://github.com/snaekobbi/system/releases/tag/v1.6.0
Country: | NL | Requirements version: | v1.5 | https://github.com/snaekobbi/requirements/releases/tag/v1.5
Date: | 2016-06-02 | CSS Specification: |  | http://snaekobbi.github.io/braille-css-spec/master/index.html
|  | Template User Guide: |  | https://github.com/daisy/pipeline-webui/wiki/Templating
Test Case 3.4:8, Support for EPUB3 as Input
Requirement ID: | 3.4:8
Description: | The system shall support EPUB 3 (conforming to the MTM procurement specification) as input. (3.4:8) | epub3-to-pef
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DE, DK, FI, NL, NO, SV
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2) dk: (formatter:dotify)(translator:nota)(grade:1¦2) fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) sv: (formatter:dotify)(translator:mtm)
Expected result:
Comments: | No input EPUB3 files yet. Should we try to collect some, or have the other agencies covered this?
Pass/Fail: | N/A
Feature Priority: | 1
Test Case 3.5:15, Support for Plain text output
Requirement ID: | 3.5:15
Description: | The system shall be able to output plain text using a user-specified braille table and form feed character. (3.5:15)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DE, DK, FI, NL, NO, SV
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2) dk: (formatter:dotify)(translator:nota)(grade:1¦2) fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) sv: (formatter:dotify)(translator:mtm)
Expected result: | To be added as unit tests.
Comments: | The system's output differs from that of Dedicon's current converter. This is because braille-utils always associates a dot pattern with the same ASCII character whereas the current converter performs a text-to-text transformation without the intermediate Unicode braille.
Pass/Fail: | Pass, but needs a real test run on our production embossers.
Feature Priority: | 1
Test Case 4.3:36, Support for Double letter spacing
Requirement ID: | 4.3:36 | http://snaekobbi.github.io/requirements/v1.5/#4.3:36
Description: | The system shall support double letter spacing, meaning adding a space between characters. Some characters should be kept together such as a capital sign and a letter. (4.3:36) | Example: https://github.com/snaekobbi/pipeline-mod-celia/blob/6a3a50e586e31b12947fba6406baa3dcb9ac548f/src/test/xprocspec/test_css_formatter.xprocspec
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | FI
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: fi: (formatter:dotify)(translator:celia) CSS Specification details: http://snaekobbi.github.io/braille-css-spec/#word-spacing-the-word-spacing-property http://snaekobbi.github.io/braille-css-spec/#h3_letter-spacing-the-letter-spacing-property
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 2
Test Case 4.3:37, Support for Contracted bralle
Requirement ID: | 4.3:37 | http://snaekobbi.github.io/requirements/v1.5/#4.3:37
Description: | The system shall support the braille code used in Denmark, Norway, Sweden and Switzerland for contracted braille. (4.3:37)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DK
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: dk: (formatter:dotify)(translator:nota)(grade:1¦2)
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 1
Test Case 4.3:38, Support for Marking of text-level semantics with braille indicators
Requirement ID: | 4.3:38 | http://snaekobbi.github.io/requirements/v1.5/#4.3:38
Description: | The system shall support marking of text-level semantics (i.e. em, strong) with braille indicators.
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DE, FI, NL, NO
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2) fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3)
Expected result: | See unit tests for the nl-NL table in liblouis.
Comments: | Needs integration of the UEB changes done by the APH.
Pass/Fail: | Fail
Feature Priority: | 1
Test Case 4.3:42, Support for non-standard hyphenation
Requirement ID: | 4.3:42 | http://snaekobbi.github.io/requirements/v1.5/#4.3:42
Description: | The system shall support non-standard hyphenation. By non-standard hyphenation we mean that the spelling of a word can change when it is hyphenated. The braille translation of a hyphenated word can only change because the spelling changes, not e.g. because it is contracted in some other way. In other words the definition of non-standard hyphenation is not “extrapolated to braille”. (4.3:42)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | NO
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3)
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 1
Test Case 4.4:48, Support for Collapsing margins
Requirement ID: | 4.4:48 | http://snaekobbi.github.io/requirements/v1.5/#4.4:48
Description: | By default margins shall be collapsing. However there shall be a way to override this behaviour. (4.4:48)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DE
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 2
Test Case 4.4:49, Support for Empty lines at top and bottom of page
Requirement ID: | 4.4:49 | http://snaekobbi.github.io/requirements/v1.5/#4.4:49
Description: | By default empty lines at the top and bottom of a page shall be suppressed. However there shall be a way to override this behaviour. (4.4:49)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DE
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result:
Comments: | NL needs this too.
Pass/Fail: | Pass (based on unit tests).
Feature Priority: | 2
Test Case 4.4:50, Support for Shrinking a block with a border to the size of its content
Requirement ID: | 4.4:50 | http://snaekobbi.github.io/requirements/v1.5/#4.4:50
Description: | There shall be the possibility of shrinking a block with a border to the size of its contents. This feature shall be supported at least for blocks with left-aligned text and no nested blocks. (4.4:50)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DE
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 2
Test Case 4.4:74, Support for single and double line spacing
Requirement ID: | 4.4:74 | http://snaekobbi.github.io/requirements/v1.5/#4.4:74
Description: | It shall be possible to configure line spacing on section level, i.e. to switch from a single line spacing section to a double line spacing section or vice-versa. (4.4:74)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | NO
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3)
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 1
Test Case 4.5:82, Support for header and footer layout change between sections
Requirement ID: | 4.5:82 | http://snaekobbi.github.io/requirements/v1.5/#4.5:82
Description: | The header and footer layout shall be able to change between sections within the document. (4.5:82)
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | DE
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 1
Test Case 4.6:88, Support for Automatic volume breaking with constraints
Requirement ID: | 4.6:88 | http://snaekobbi.github.io/requirements/v1.5/#4.6:88
Description: | The system shall be able to perform automatic volume breaking with constraints. It shall be possible to precisely tweak the algorithm. It shall take values for minimal and maximal number of pages per volume. It shall support special ranges for the first and last volume of sections. The algorithm shall take into account that certain points in the book are better suited for being the start of a new volume than other points and that certain sections belong in certain volumes. (4.6:88)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DK, NO
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. set Optional parameters 5. click "Start job" 6. see storage Result/Output Directory file 7.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. set Optional parameters 5. click Start job 6. see storage Result/Output Directory file 7. verify output result | Transformer query: no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3)
Expected result:
Comments: | Maybe the distinction between print pages, braille pages and braille sheets could be clarified a bit, especially with regard to duplex printing, stapling versus bound books, etc.
Pass/Fail:
Feature Priority: | 1
Test Case 4.6:93, Support for Manual user control over volume breaking
Requirement ID: | 4.6:93 | http://snaekobbi.github.io/requirements/v1.5/#4.6:93
Description: | The user shall have some form of manual control over volume breaking. (4.6:93)
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | DE
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 3
Test Case 4.7:96, Support for Automatic insertion of content that is not present in the source
Requirement ID: | 4.7:96 | http://snaekobbi.github.io/requirements/v1.5/#4.7:96
Description: | The system shall support automatic insertion of content that is not present in the source. Examples include: ◦ boilerplate text inserted e.g. on the title page, ◦ metadata and details about the production process, ◦ automatic transcriber notes that give information about omitted or moved content, about how tables are rendered, ◦ etc. (4.7:96)
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | DE, DK, FI, NL, NO, SV
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2) dk: (formatter:dotify)(translator:nota)(grade:1¦2) fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) sv: (formatter:dotify)(translator:mtm)
Expected result: | See unit tests for boilerplate text.
Comments: | Passes, but probably needs some last refinements.
Pass/Fail: | Pass
Feature Priority: | 1
Test Case 4.7:102, Support for Evaluating certain variables and counters at so-called "fields"
Requirement ID: | 4.7:102 | http://snaekobbi.github.io/requirements/v1.5/#4.7:102
Description: | The system shall be able to evaluate certain variables and counters at so-called "fields", for example on the title page or in the page header or footer. Supported variables shall include at least the current braille page number, the current print page number or range of print pages contained in the current braille page, the current volume number, the total number of volumes, the total number of braille pages or sheets contained in the current volume or book, the current chapter title, the current chapter number, and the date. (4.7:102)
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | DE, NO
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2) dk: (formatter:dotify)(translator:nota)(grade:1¦2) fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) sv: (formatter:dotify)(translator:mtm)
Expected result: | See unit tests for pagination.
Comments: | Showing print page ranges is broken, e.g. instead of '2 - 4' only '4' is shown.
Pass/Fail: | Fail
Feature Priority: | 1

## Sprint_10 Test cases_NO
Test protocol "Braille in DAISY Pipeline 2"
Tester: | Kari Rudjord | Software build and release notes: | v1.6.0 | https://github.com/snaekobbi/system/releases/tag/v1.6.0
Country: | Norway | Requirements version: | v1.5 | https://github.com/snaekobbi/requirements/releases/tag/v1.5
Date: | 2016-06-08 | CSS Specification: |  | http://snaekobbi.github.io/braille-css-spec/master/index.html
|  | Template User Guide: |  | https://github.com/daisy/pipeline-webui/wiki/Templating
Test Case 3.4:8, Support for EPUB3 as Input
Requirement ID: | 3.4:8 | Deadline neste uke (9.6)
Description: | The system shall support EPUB 3 (conforming to the MTM procurement specification) as input. (3.4:8) | epub3-to-pef
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DE, DK, FI, NL, NO, SV
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2) dk: (formatter:dotify)(translator:nota)(grade:1¦2) fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) sv: (formatter:dotify)(translator:mtm)
Expected result:
Comments:
Pass/Fail: | Fail | "Entity too large" - problem with large files
Feature Priority: | 1
Test Case 3.5:15, Support for Plain text output
Requirement ID: | 3.5:15
Description: | The system shall be able to output plain text using a user-specified braille table and form feed character. (3.5:15)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DE, DK, FI, NL, NO, SV
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2) dk: (formatter:dotify)(translator:nota)(grade:1¦2) fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) sv: (formatter:dotify)(translator:mtm)
Expected result:
Comments:
Pass/Fail: | Not tested
Feature Priority: | 1
Test Case 4.3:36, Support for Double letter spacing
Requirement ID: | 4.3:36 | http://snaekobbi.github.io/requirements/v1.5/#4.3:36
Description: | The system shall support double letter spacing, meaning adding a space between characters. Some characters should be kept together such as a capital sign and a letter. (4.3:36) | Example: https://github.com/snaekobbi/pipeline-mod-celia/blob/6a3a50e586e31b12947fba6406baa3dcb9ac548f/src/test/xprocspec/test_css_formatter.xprocspec
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | FI
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: fi: (formatter:dotify)(translator:celia) CSS Specification details: http://snaekobbi.github.io/braille-css-spec/#word-spacing-the-word-spacing-property http://snaekobbi.github.io/braille-css-spec/#h3_letter-spacing-the-letter-spacing-property
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 2
Test Case 4.3:37, Support for Contracted bralle
Requirement ID: | 4.3:37 | http://snaekobbi.github.io/requirements/v1.5/#4.3:37
Description: | The system shall support the braille code used in Denmark, Norway, Sweden and Switzerland for contracted braille. (4.3:37)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DK
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: dk: (formatter:dotify)(translator:nota)(grade:1¦2)
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 1
Test Case 4.3:38, Support for Marking of text-level semantics with braille indicators
Requirement ID: | 4.3:38 | http://snaekobbi.github.io/requirements/v1.5/#4.3:38
Description: | The system shall support marking of text-level semantics (i.e. em, strong) with braille indicators.
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DE, FI, NL, NO
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2) fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3)
Expected result:
Comments:
Pass/Fail: | Pass
Feature Priority: | 1
Test Case 4.3:42, Support for non-standard hyphenation
Requirement ID: | 4.3:42 | http://snaekobbi.github.io/requirements/v1.5/#4.3:42
Description: | The system shall support non-standard hyphenation. By non-standard hyphenation we mean that the spelling of a word can change when it is hyphenated. The braille translation of a hyphenated word can only change because the spelling changes, not e.g. because it is contracted in some other way. In other words the definition of non-standard hyphenation is not “extrapolated to braille”. (4.3:42)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | NO
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3)
Expected result: | PASS
Comments:
Pass/Fail:
Feature Priority: | 1
Test Case 4.4:48, Support for Collapsing margins
Requirement ID: | 4.4:48 | http://snaekobbi.github.io/requirements/v1.5/#4.4:48
Description: | By default margins shall be collapsing. However there shall be a way to override this behaviour. (4.4:48)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DE
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 2
Test Case 4.4:49, Support for Empty lines at top and bottom of page
Requirement ID: | 4.4:49 | http://snaekobbi.github.io/requirements/v1.5/#4.4:49
Description: | By default empty lines at the top and bottom of a page shall be suppressed. However there shall be a way to override this behaviour. (4.4:49)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DE
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 2
Test Case 4.4:50, Support for Shrinking a block with a border to the size of its content
Requirement ID: | 4.4:50 | http://snaekobbi.github.io/requirements/v1.5/#4.4:50
Description: | There shall be the possibility of shrinking a block with a border to the size of its contents. This feature shall be supported at least for blocks with left-aligned text and no nested blocks. (4.4:50)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DE
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 2
Test Case 4.4:74, Support for single and double line spacing
Requirement ID: | 4.4:74 | http://snaekobbi.github.io/requirements/v1.5/#4.4:74
Description: | It shall be possible to configure line spacing on section level, i.e. to switch from a single line spacing section to a double line spacing section or vice-versa. (4.4:74)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | NO
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3)
Expected result:
Comments:
Pass/Fail: | not ready for test
Feature Priority: | 1
Test Case 4.5:82, Support for header and footer layout change between sections
Requirement ID: | 4.5:82 | http://snaekobbi.github.io/requirements/v1.5/#4.5:82
Description: | The header and footer layout shall be able to change between sections within the document. (4.5:82)
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | DE
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 1
Test Case 4.6:88, Support for Automatic volume breaking with constraints
Requirement ID: | 4.6:88 | http://snaekobbi.github.io/requirements/v1.5/#4.6:88
Description: | The system shall be able to perform automatic volume breaking with constraints. It shall be possible to precisely tweak the algorithm. It shall take values for minimal and maximal number of pages per volume. It shall support special ranges for the first and last volume of sections. The algorithm shall take into account that certain points in the book are better suited for being the start of a new volume than other points and that certain sections belong in certain volumes. (4.6:88)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DK, NO
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. set Optional parameters 5. click "Start job" 6. see storage Result/Output Directory file 7.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. set Optional parameters 5. click Start job 6. see storage Result/Output Directory file 7. verify output result | Transformer query: no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3)
Expected result:
Comments:
Pass/Fail: | not ready for test
Feature Priority: | 1
Test Case 4.6:93, Support for Manual user control over volume breaking
Requirement ID: | 4.6:93 | http://snaekobbi.github.io/requirements/v1.5/#4.6:93
Description: | The user shall have some form of manual control over volume breaking. (4.6:93)
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | DE
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result:
Comments:
Pass/Fail: | not ready for test
Feature Priority: | 3
Test Case 4.7:96, Support for Automatic insertion of content that is not present in the source
Requirement ID: | 4.7:96 | http://snaekobbi.github.io/requirements/v1.5/#4.7:96
Description: | The system shall support automatic insertion of content that is not present in the source. Examples include: ◦ boilerplate text inserted e.g. on the title page, ◦ metadata and details about the production process, ◦ automatic transcriber notes that give information about omitted or moved content, about how tables are rendered, ◦ etc. (4.7:96)
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | DE, DK, FI, NL, NO, SV
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2) dk: (formatter:dotify)(translator:nota)(grade:1¦2) fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) sv: (formatter:dotify)(translator:mtm)
Expected result:
Comments:
Pass/Fail: | Pass | total number of sheets, title page layout
Feature Priority: | 1
Test Case 4.7:102, Support for Evaluating certain variables and counters at so-called "fields"
Requirement ID: | 4.7:102 | http://snaekobbi.github.io/requirements/v1.5/#4.7:102
Description: | The system shall be able to evaluate certain variables and counters at so-called "fields", for example on the title page or in the page header or footer. Supported variables shall include at least the current braille page number, the current print page number or range of print pages contained in the current braille page, the current volume number, the total number of volumes, the total number of braille pages or sheets contained in the current volume or book, the current chapter title, the current chapter number, and the date. (4.7:102)
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | DE, NO
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2) dk: (formatter:dotify)(translator:nota)(grade:1¦2) fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) sv: (formatter:dotify)(translator:mtm)
Expected result:
Comments:
Pass/Fail: | Pass | total number of sheets
Feature Priority: | 1

## Sprint_10 Test cases_SE
Test protocol "Braille in DAISY Pipeline 2"
Tester: | Björn Westling et al. | Software build and release notes: | v1.6.0 | https://github.com/snaekobbi/system/releases/tag/v1.6.0
Country: | SE | Requirements version: | v1.5 | https://github.com/snaekobbi/requirements/releases/tag/v1.5
Date: | 2016-06-10 | CSS Specification: |  | http://snaekobbi.github.io/braille-css-spec/master/index.html
|  | Template User Guide: |  | https://github.com/daisy/pipeline-webui/wiki/Templating
Test Case 3.4:8, Support for EPUB3 as Input
Requirement ID: | 3.4:8
Description: | The system shall support EPUB 3 (conforming to the MTM procurement specification) as input. (3.4:8) | epub3-to-pef
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DE, DK, FI, NL, NO, SV
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2) dk: (formatter:dotify)(translator:nota)(grade:1¦2) fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) sv: (formatter:dotify)(translator:mtm)
Expected result:
Comments: | This functionality has not been implemented.
Pass/Fail: | FAIL
Feature Priority: | 1
Test Case 3.5:15, Support for Plain text output
Requirement ID: | 3.5:15
Description: | The system shall be able to output plain text using a user-specified braille table and form feed character. (3.5:15)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DE, DK, FI, NL, NO, SV
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2) dk: (formatter:dotify)(translator:nota)(grade:1¦2) fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) sv: (formatter:dotify)(translator:mtm)
Expected result:
Comments: | HAS NOT BEEN TESTED
Pass/Fail:
Feature Priority: | 1
Test Case 4.3:36, Support for Double letter spacing
Requirement ID: | 4.3:36 | http://snaekobbi.github.io/requirements/v1.5/#4.3:36
Description: | The system shall support double letter spacing, meaning adding a space between characters. Some characters should be kept together such as a capital sign and a letter. (4.3:36) | Example: https://github.com/snaekobbi/pipeline-mod-celia/blob/6a3a50e586e31b12947fba6406baa3dcb9ac548f/src/test/xprocspec/test_css_formatter.xprocspec
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | FI
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: fi: (formatter:dotify)(translator:celia) CSS Specification details: http://snaekobbi.github.io/braille-css-spec/#word-spacing-the-word-spacing-property http://snaekobbi.github.io/braille-css-spec/#h3_letter-spacing-the-letter-spacing-property
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 2
Test Case 4.3:37, Support for Contracted bralle
Requirement ID: | 4.3:37 | http://snaekobbi.github.io/requirements/v1.5/#4.3:37
Description: | The system shall support the braille code used in Denmark, Norway, Sweden and Switzerland for contracted braille. (4.3:37)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DK
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: dk: (formatter:dotify)(translator:nota)(grade:1¦2)
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 1
Test Case 4.3:38, Support for Marking of text-level semantics with braille indicators
Requirement ID: | 4.3:38 | http://snaekobbi.github.io/requirements/v1.5/#4.3:38
Description: | The system shall support marking of text-level semantics (i.e. em, strong) with braille indicators.
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DE, FI, NL, NO
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2) fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3)
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 1
Test Case 4.3:42, Support for non-standard hyphenation
Requirement ID: | 4.3:42 | http://snaekobbi.github.io/requirements/v1.5/#4.3:42
Description: | The system shall support non-standard hyphenation. By non-standard hyphenation we mean that the spelling of a word can change when it is hyphenated. The braille translation of a hyphenated word can only change because the spelling changes, not e.g. because it is contracted in some other way. In other words the definition of non-standard hyphenation is not “extrapolated to braille”. (4.3:42)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | NO
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3)
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 1
Test Case 4.4:48, Support for Collapsing margins
Requirement ID: | 4.4:48 | http://snaekobbi.github.io/requirements/v1.5/#4.4:48
Description: | By default margins shall be collapsing. However there shall be a way to override this behaviour. (4.4:48)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DE
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 2
Test Case 4.4:49, Support for Empty lines at top and bottom of page
Requirement ID: | 4.4:49 | http://snaekobbi.github.io/requirements/v1.5/#4.4:49
Description: | By default empty lines at the top and bottom of a page shall be suppressed. However there shall be a way to override this behaviour. (4.4:49)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DE
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 2
Test Case 4.4:50, Support for Shrinking a block with a border to the size of its content
Requirement ID: | 4.4:50 | http://snaekobbi.github.io/requirements/v1.5/#4.4:50
Description: | There shall be the possibility of shrinking a block with a border to the size of its contents. This feature shall be supported at least for blocks with left-aligned text and no nested blocks. (4.4:50)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DE
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 2
Test Case 4.4:74, Support for single and double line spacing
Requirement ID: | 4.4:74 | http://snaekobbi.github.io/requirements/v1.5/#4.4:74
Description: | It shall be possible to configure line spacing on section level, i.e. to switch from a single line spacing section to a double line spacing section or vice-versa. (4.4:74)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | NO
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3)
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 1
Test Case 4.5:82, Support for header and footer layout change between sections
Requirement ID: | 4.5:82 | http://snaekobbi.github.io/requirements/v1.5/#4.5:82
Description: | The header and footer layout shall be able to change between sections within the document. (4.5:82)
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | DE
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 1
Test Case 4.6:88, Support for Automatic volume breaking with constraints
Requirement ID: | 4.6:88 | http://snaekobbi.github.io/requirements/v1.5/#4.6:88
Description: | The system shall be able to perform automatic volume breaking with constraints. It shall be possible to precisely tweak the algorithm. It shall take values for minimal and maximal number of pages per volume. It shall support special ranges for the first and last volume of sections. The algorithm shall take into account that certain points in the book are better suited for being the start of a new volume than other points and that certain sections belong in certain volumes. (4.6:88)
Pre-requisites: | Logged in to Web UI, valid country requirement
Testing Agencies: | DK, NO
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. set Optional parameters 5. click "Start job" 6. see storage Result/Output Directory file 7.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. set Optional parameters 5. click Start job 6. see storage Result/Output Directory file 7. verify output result | Transformer query: no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3)
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 1
Test Case 4.6:93, Support for Manual user control over volume breaking
Requirement ID: | 4.6:93 | http://snaekobbi.github.io/requirements/v1.5/#4.6:93
Description: | The user shall have some form of manual control over volume breaking. (4.6:93)
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | DE
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2)
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 3
Test Case 4.7:96, Support for Automatic insertion of content that is not present in the source
Requirement ID: | 4.7:96 | http://snaekobbi.github.io/requirements/v1.5/#4.7:96
Description: | The system shall support automatic insertion of content that is not present in the source. Examples include: ◦ boilerplate text inserted e.g. on the title page, ◦ metadata and details about the production process, ◦ automatic transcriber notes that give information about omitted or moved content, about how tables are rendered, ◦ etc. (4.7:96)
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | DE, DK, FI, NL, NO, SV
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2) dk: (formatter:dotify)(translator:nota)(grade:1¦2) fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) sv: (formatter:dotify)(translator:mtm)
Expected result:
Comments: | The MTM script provides functionality on boilerplate text and metadata insertion, but no functionality on automatic transcriber notes.
Pass/Fail: | PASS
Feature Priority: | 1
Test Case 4.7:102, Support for Evaluating certain variables and counters at so-called "fields"
Requirement ID: | 4.7:102 | http://snaekobbi.github.io/requirements/v1.5/#4.7:102
Description: | The system shall be able to evaluate certain variables and counters at so-called "fields", for example on the title page or in the page header or footer. Supported variables shall include at least the current braille page number, the current print page number or range of print pages contained in the current braille page, the current volume number, the total number of volumes, the total number of braille pages or sheets contained in the current volume or book, the current chapter title, the current chapter number, and the date. (4.7:102)
Pre-requisites: | Logged in to Web UI, valid country requirement
Agencies/Test data: | DE, NO
Steps: | Create Job without Template: 0. click "Create Job" tab in the navigation bar 1. Upload Files to include and process 2. select Script to run 3. set Options 4. click "Start job" 5. see storage Result/Output Directory file 6.verify output result Create Job based on Template: 0. click "Templates" tab in the navigation bar 1. click "New job" for a template in the list 2. upload any additional files 3. set mandatory Options 4. click Start job 5. see storage Result/Output Directory file 6. verify output result | Transformer query: de: (formatter:dotify)(translator:sbs)(grade:0¦1¦2) dk: (formatter:dotify)(translator:nota)(grade:1¦2) fi: (formatter:dotify)(translator:celia) nl: (formatter:dotify)(translator:dedicon) no: (formatter:dotify)(translator:nlb)(grade:0¦1¦2¦3) sv: (formatter:dotify)(translator:mtm)
Expected result:
Comments:
Pass/Fail:
Feature Priority: | 1
Requirement ID: | 4.3:35C
Description: | The system shall support the possibility to leave out capital signs in some products.
Expected result:
Comments:
Pass/Fail: | PASS
Feature Priority: | 1
Requirement ID: | 4.3:38
Description: | The system shall support marking of text-level semantics with braille indicators.
Expected result:
Comments:
Pass/Fail: | PASS
Feature Priority: | 1
Requirement ID: | 4.4:58
Description: | There shall be the option to render a table in matrix format…
Expected result:
Comments: | TABLES IN MATRIX FORMAT: the rendition is working very well in most cases, a little less in others. A need for optimization with time is identified, together with more attention to markup improvements in the source files, many erros found, e.g. lack of markup of column and row headings.
Pass/Fail: | PASS
Feature Priority: | 1
Requirement ID: | 4.8:106
Description: | The system shall provide the possibility of rendering print page breaks as marks in the left margin, taking them out of the normal text flow…
Expected result:
Comments: | NOTE THAT MTM has chosen to implement 4.8:106 instead of 4.8.105. RESULT: works fine, apart from a few occuring errors where marks in the left margin are shown on the line prior to the print page breaks. Needs to be fixed.
Pass/Fail: | FAIL
Feature Priority: | 1
Requirement ID: | 4.3:45
Description: | The user shall have fine-grained control over the translation…
Expected result:
Comments: | Concerning the possibility to choose how to convert letters with diacritics: this functionality has not been implemented.
Pass/Fail: | FAIL
Feature Priority: | 1
Requirement ID: | 4.9:113
Description: | The user shall be able to monitor jobs
Expected result:
Comments: | Error messages still do not work properly, and are not understandable. The user does not understand why things go wrong.
Pass/Fail: | FAIL
Feature Priority: | 1
NÅGRA ANDRA KOMMENTARER TILL JOEL:
ENKELSIDIGT TRYCK - simplex: sidnumreringen alternerar som om det vore dubbelsidigt - FEL. (se P11111)
TITLEPAGE (frontmatter level1 class titlepage) skrivs ut i början, liksom en level1_3 med bibliografisk information. Se boken P22222. FEL I UPPMÄRKNING.
RUBRIKER H1: c-linje som understrykning. Bara för LL-böcker eller minns jag fel??? Se boken P22222.
Tom sida före kapitelrubriker? Fel? Se sidan 6. Dubbelt radavstånd gör att avstånd under rad ibland genererar en ny sida.