## Celia
Feature |  |  | State | Comments | Include in acceptance test (+ comments)
3.4:8 |  | The system shall support EPUB 3 as input. | Under development
4.1:25 | 1 | The system shall support editing on block level in order to fix wrong translations… | To do
4.1:26 | 2 | The system shall support editing beyond block level… | To do
4.1:27 | 3 | The system shall be able to merge changes made in the original text with changes made previously in the braille version… | To do
4.1:28 | 3 | The system shall be able to produce synchronization data for various intermediary and output files… | To do
4.1:29 | 3 | The system shall provide a graphical user interface for editing an intermediary braille file. | To do
4.1:30 | 3 | The user interface shall provide a side-by-side view of the original text and braille… | To do
4.1:31 | 3 | There shall be support for inserting braille characters using 6/8 keys on the keyboard. | To do
4.2:32 | 1 | The system shall be able to output various e-braille formats. | Planned for sprint 9
4.2:33 | 1 | The system shall support a new e-braille format. | Planned for sprint 9
4.3:34B | 1 | The system shall be easily extended with new languages - for uncontracted braille… | To do | Not easily testable
4.3:34C | 1 | The system shall support the braille code used in the Netherlands for uncontracted braille. | To do | Under development, see 4.3:34
4.3:34 | 1 | The system shall support the braille code used in Denmark, Finland, Norway, Sweden, Switzerland and the Netherlands for uncontracted braille. | Ready for test | Has been tested a lot implicitly, optimization needed for German (and for emphasis in Dutch: 4.3:38) | yes
4.3:35C | 1 | The system shall support the possibility to leave out capital signs in some products. | Done
4.3:35B | 1 | The system shall support the braille code used in the Netherlands for 8-dot braille. | To do | No detailed specifications
4.3:35 | 1 | The system shall support the braille code used in Denmark, Finland, Norway, Sweden and Switzerland for 8-dot braille. | On hold | No detailed specifications
4.3:36 | 2 | The system shall support double letter spacing… | On hold | Needs optimization (wrt hyphenation) | yes
4.3:37B | 1 | The system shall be easily extended with new languages - for contracted braille… | To do | Not easily testable
4.3:37C | 1 | The system shall support the braille code used in the Netherlands for contracted braille. | Cancelled
4.3:37 | 1 | The system shall support the braille code used in Denmark, Norway, Sweden and Switzerland for contracted braille. | Under test | Has been tested a lot implicitly, optimization needed for German
4.3:38 | 1 | The system shall support marking of text-level semantics with braille indicators. | On hold | Under development, new release of Liblouis needed
4.3:39 | 1 | The system shall support marking of visual text styling/typography with braille indicators… | To do | Doesn't seem to be a requirement for anyone after all
4.3:40 | 1 | The system shall have a flexible and configurable mapping from markup to braille indicators… | To do | Ready for test (smoke test required before acceptance test) | yes
4.3:41 | 1 | The system shall be able to perform automatic hyphenation for uncontracted and contracted braille. | On hold | Tested that hyphenation works, but optimization needed for some (workflow has been suggested to improve hyphenation over time, real usage is required for this) | yes
4.3:42 | 1 | The system shall support non-standard hyphenation… | Under development
4.3:43 | 2 | When automatic hyphenation is enabled, it shall be possible to exclude certain elements… | To do | Ready for test (smoke test required before acceptance test)
4.3:44 | 1 | The user shall be able to make a top-level configuration… | Under development
4.3:45 | 3 | The user shall have fine-grained control over the translation… | To do | Framework in place, agency-specific code required, no detailed specifications
4.4:46 | 1 | The system shall have support for top, right, bottom and left margins on blocks. | Done
4.4:47 | 1 | The system shall have support for top, right, bottom and left borders and padding on blocks. | Done
4.4:48 | 2 | By default margins shall be collapsing. However there shall be a way to override this behaviour. | On hold
4.4:49 | 2 | By default empty lines at the top and bottom of a page shall be suppressed. However there shall be a way to override this behaviour. | To do | Decided to drop this for now
4.4:50 | 2 | There shall be the possibility of shrinking a block with a border to the size of its contents… | To do | Possibly implement with a OBFL table
4.4:51 | 1 | The system shall have support for first line indentation. | Done |  | yes
4.4:52 | 1 | Besides left-aligned text, the system shall have support for centered and right-aligned text. | Done
4.4:53 | 1 | The system shall support block alignment relative to a vertical position on the page. | Done
4.4:54 | 1 | The system shall by default handle whitespace characters in the source XML according to the following rules… | Ready for test | Ready for acceptance test
4.4:55 | 2 | The user shall be able to override the default handling of whitespace for certain elements… | Ready for test | Ready for acceptance test (except for German: optimization + smoke test needed)
4.4:56 | 2 | The system shall provide a way to control the layout of each table separately. | On hold | Ready for acceptance test (only documentation missing)
4.4:57 | 1 | There shall be the option to reformat a table into a list… | Under test |  | yes
4.4:58 | 1 | There shall be the option to render a table in matrix format… | Under development
4.4:59 | 2 | When a table in matrix format spans multiple pages, there shall be the possibility of repeating the table heading at the top of each page. | To do | Dotify refactoring required
4.4:60 | 2 | There shall be the possibility of transposing tables… | To do | Tables as lists: done and tested, matrix tables: to do
4.4:61 | 2 | The system shall provide a table layout fallback mechanism… | Under development
4.4:62 | 3 | The system shall be able to cope with column- and rowspan in tables… | To do | Tables as lists: done and tested, matrix tables: ready for test
4.4:63 | 3 | There shall be the option to render a big or complex table in matrix format… | To do
4.4:64 | 3 | There shall be the option to render a wide table on facing pages. | To do
4.4:65 | 1 | The system shall be able to render tables of contents, list of images, index, glossaries, etc. in a two-column format… | Done |  | yes
4.4:66 | 1 | The system shall support positioning of notes at the bottom of the page on which they are being referenced. | Under development
4.4:67 | 1 | The system shall support collecting of notes either at the end of each volume, or at the end of the entire book. | Under development
4.4:68 | 1 | The system shall provide a notes layout fallback mechanism… | To do
4.4:69 | 3 | The system shall support inline rendering of notes right after the note reference… | Under development
4.4:70 | 3 | The system shall support rendering of certain elements such as line numbers in the left margin, taking them out of the normal text flow… | To do
4.4:71 | 3 | The system shall provide the possibility of moving certain content that hinders readability… | To do
4.4:72 | 3 | The system shall provide the possibility of omitting certain content. | To do
4.4:73 | 2 | There shall be the possibility of rendering certain elements such as line numbers in the left margin, not taking them out of the normal text flow… | To do
4.4:74 | 1 | The system shall support single and double line spacing. | Done |  | yes
4.4:75 | 1 | When printing double-sided with line spacing greater than 1, printed lines shall alternate on odd and even pages. | Done
4.4:76 | 3 | The system shall support line spacing between single and double. | Cancelled
4.5:78 | 1 | The user shall have control over page breaking… | Done |  | yes
4.5:79 | 3 | The system shall provide the option to disable page breaking… | To do
4.5:80 | 1 | The user shall have control over the page dimensions and the size of page margins. | Done |  | yes
4.5:81 | 1 | There shall be support for content in the header and footer of pages… | Done |  | yes
4.5:82 | 1 | The header and footer layout shall be able to change between sections within the document. | Done
4.5:83 | 3 | The system shall support flowing of text into the header or footer… | To do
4.5:84 | 1 | When printing double-sided, there shall be support for hard page breaks that jump to the next right- or left-hand page. | On hold | Tested, decided to omit 'left-hand page' for now
4.5:85 | 1 | When printing double-sided, the system shall allow the page layout to differ between left- and right-hand pages. | Done |  | yes
4.5:86 | 3 | Support for mixed braille and ink on the cover page… | To do
4.5:87 | 3 | Support for interlining braille and ink, or combining braille and ink on facing pages… | To do
4.6:88 | 1 | The system shall be able to perform automatic volume breaking… | Under test | To do: advanced volume breaking | yes
4.6:89 | 1 | The system shall provide the possibility of repeating certain content in several volumes. | Ready for test
4.6:90 | 1 | The system shall support trimming down of a table of contents to a volume-scope table of contents… | Done |  | yes
4.6:91 | 1 | In the case of an extended table of contents that is not trimmed down, it shall be possible to group entries according to volume… | Under test | Issue fixed and ready for re-test
4.6:92 | 1 | In the case of endnotes being collected at the end of a book, it shall be possible to group the notes according to volume… | Under development
4.6:93 | 3 | The user shall have some form of manual control over volume breaking. | Planned for sprint 9
4.7:94 | 1 | The system shall support formatting of numbers and other variables in a wide selection of formats… | On hold | Partly implemented
4.7:95 | 2 | The system shall support insertion of content that is not present in the source, through configuration… | To do | Ready for test (smoke test required before acceptance test)
4.7:96 | 1 | The system shall support automatic insertion of content that is not present in the source… | Under development | NLB: done and tested, other: under development | yes?
4.7:97 | 1 | The system shall be able to perform automatic numbering of braille pages and volumes. | On hold | Pages: done and tested, volumes: ready for test | yes
4.7:98 | 1 | The system shall be able to perform automatic numbering on type ol lists… | To do | Ready for test (smoke test required before acceptance test)
4.7:99 | 2 | The system shall support resetting of braille page numbering at the start of major sections… | Done
4.7:100 | 3 | The system shall be able to perform automatic numbering of notes… | To do
4.7:101 | 3 | The system shall support resetting braille page numbering for each volume. | To do
4.7:102 | 1 | The system shall be able to evaluate certain variables and counters at so-called fields… | Under test | Needs optimization
4.7:103 | 1 | The system shall support insertion of certain variables and counters at references evaluated at the target… | To do | Tested implicitly (generated table of content), done
4.7:104 | 3 | The system shall support insertion of certain variables and counters at referenced items evaluated at the reference… | To do
4.8:105 | 1 | The system shall provide the possibility of rendering print page breaks as full lines across the width of the page… | On hold | Needs optimization, not implemented for MTM | yes
4.8:106 | 2 | The system shall provide the possibility of rendering print page breaks as marks in the left margin, taking them out of the normal text flow… | Done |  | yes
4.8:107 | 2 | The system shall support skipping print page breaks when no text precedes or follows on the same braille page. | On hold
4.9:108 | 1 | The system shall support templates for different products… | Done |  | yes
4.9:109 | 1 | The system shall support templates for different end user groups. | Done
4.9:110 | 1 | Users shall be able to reuse templates. | Done |  | yes
4.9:111 | 1 | Certain users shall be able to create templates. | Done |  | yes
4.9:112 | 1 | The system shall save jobs so that e.g. a job history can be showed, and jobs can be rerun. | Done |  | yes
4.9:113 | 1 | The user shall be able to monitor jobs… | Done |  | yes
4.9:114 | 2 | The system shall provide the user with help and guidance for creating templates. | On hold | Framework for script documentation in place, more actual documentation needed | yes
4.9:115 | 1 | The system shall provide a graphical user interface for creating and monitoring jobs. | To do | Tested implicitly, done
4.7:117 | 3 | The system shall support the possibility to integrate tactile drawings in braille. | To do
4.7:118 | 3 | The system shall support the creation of symbols lists, when characters have different meaning than normally… | To do
4.10:119 | 3 | The system shall support giving marked up mathematics code in ASCII-Math an output according to the mathematical braille code in the Netherlands. | To do

## Dedicon
Still pending

## Nota
Feature |  |  | State | Comments | Include in acceptance test (+ comments)
3.4:8 |  | The system shall support EPUB 3 as input. | Under development |  | Yes
4.1:25 | 1 | The system shall support editing on block level in order to fix wrong translations… | To do
4.1:26 | 2 | The system shall support editing beyond block level… | To do
4.1:27 | 3 | The system shall be able to merge changes made in the original text with changes made previously in the braille version… | To do
4.1:28 | 3 | The system shall be able to produce synchronization data for various intermediary and output files… | To do
4.1:29 | 3 | The system shall provide a graphical user interface for editing an intermediary braille file. | To do
4.1:30 | 3 | The user interface shall provide a side-by-side view of the original text and braille… | To do
4.1:31 | 3 | There shall be support for inserting braille characters using 6/8 keys on the keyboard. | To do
4.2:32 | 1 | The system shall be able to output various e-braille formats. | Planned for sprint 9
4.2:33 | 1 | The system shall support a new e-braille format. | Planned for sprint 9
4.3:34B | 1 | The system shall be easily extended with new languages - for uncontracted braille… | To do | Not easily testable
4.3:34C | 1 | The system shall support the braille code used in the Netherlands for uncontracted braille. | To do | Under development, see 4.3:34
4.3:34 | 1 | The system shall support the braille code used in Denmark, Finland, Norway, Sweden, Switzerland and the Netherlands for uncontracted braille. | Ready for test | Has been tested a lot implicitly, optimization needed for German (and for emphasis in Dutch: 4.3:38) | Yes
4.3:35C | 1 | The system shall support the possibility to leave out capital signs in some products. | Done
4.3:35B | 1 | The system shall support the braille code used in the Netherlands for 8-dot braille. | To do | No detailed specifications
4.3:35 | 1 | The system shall support the braille code used in Denmark, Finland, Norway, Sweden and Switzerland for 8-dot braille. | On hold | No detailed specifications
4.3:36 | 2 | The system shall support double letter spacing… | On hold | Needs optimization (wrt hyphenation)
4.3:37B | 1 | The system shall be easily extended with new languages - for contracted braille… | To do | Not easily testable
4.3:37C | 1 | The system shall support the braille code used in the Netherlands for contracted braille. | Cancelled
4.3:37 | 1 | The system shall support the braille code used in Denmark, Norway, Sweden and Switzerland for contracted braille. | Under test | Has been tested a lot implicitly, optimization needed for German | Yes
4.3:38 | 1 | The system shall support marking of text-level semantics with braille indicators. | On hold | Under development, new release of Liblouis needed | Yes – certainly needs testing at some point, even if it can't be done just now
4.3:39 | 1 | The system shall support marking of visual text styling/typography with braille indicators… | To do | Doesn't seem to be a requirement for anyone after all
4.3:40 | 1 | The system shall have a flexible and configurable mapping from markup to braille indicators… | To do | Ready for test (smoke test required before acceptance test) | Yes
4.3:41 | 1 | The system shall be able to perform automatic hyphenation for uncontracted and contracted braille. | On hold | Tested that hyphenation works, but optimization needed for some (workflow has been suggested to improve hyphenation over time, real usage is required for this) | Yes
4.3:42 | 1 | The system shall support non-standard hyphenation… | Under development
4.3:43 | 2 | When automatic hyphenation is enabled, it shall be possible to exclude certain elements… | To do | Ready for test (smoke test required before acceptance test)
4.3:44 | 1 | The user shall be able to make a top-level configuration… | Under development |  | Yes
4.3:45 | 3 | The user shall have fine-grained control over the translation… | To do | Framework in place, agency-specific code required, no detailed specifications
4.4:46 | 1 | The system shall have support for top, right, bottom and left margins on blocks. | Done |  | Yes
4.4:47 | 1 | The system shall have support for top, right, bottom and left borders and padding on blocks. | Done |  | Yes – padding only
4.4:48 | 2 | By default margins shall be collapsing. However there shall be a way to override this behaviour. | On hold
4.4:49 | 2 | By default empty lines at the top and bottom of a page shall be suppressed. However there shall be a way to override this behaviour. | To do | Decided to drop this for now
4.4:50 | 2 | There shall be the possibility of shrinking a block with a border to the size of its contents… | To do | Possibly implement with a OBFL table
4.4:51 | 1 | The system shall have support for first line indentation. | Done |  | Yes
4.4:52 | 1 | Besides left-aligned text, the system shall have support for centered and right-aligned text. | Done |  | Yes
4.4:53 | 1 | The system shall support block alignment relative to a vertical position on the page. | Done |  | Yes
4.4:54 | 1 | The system shall by default handle whitespace characters in the source XML according to the following rules… | Ready for test | Ready for acceptance test | Yes
4.4:55 | 2 | The user shall be able to override the default handling of whitespace for certain elements… | Ready for test | Ready for acceptance test (except for German: optimization + smoke test needed) | Yes
4.4:56 | 2 | The system shall provide a way to control the layout of each table separately. | On hold | Ready for acceptance test (only documentation missing) | Yes
4.4:57 | 1 | There shall be the option to reformat a table into a list… | Under test |  | Yes
4.4:58 | 1 | There shall be the option to render a table in matrix format… | Under development
4.4:59 | 2 | When a table in matrix format spans multiple pages, there shall be the possibility of repeating the table heading at the top of each page. | To do | Dotify refactoring required
4.4:60 | 2 | There shall be the possibility of transposing tables… | To do | Tables as lists: done and tested, matrix tables: to do | Yes
4.4:61 | 2 | The system shall provide a table layout fallback mechanism… | Under development
4.4:62 | 3 | The system shall be able to cope with column- and rowspan in tables… | To do | Tables as lists: done and tested, matrix tables: ready for test | Yes
4.4:63 | 3 | There shall be the option to render a big or complex table in matrix format… | To do
4.4:64 | 3 | There shall be the option to render a wide table on facing pages. | To do
4.4:65 | 1 | The system shall be able to render tables of contents, list of images, index, glossaries, etc. in a two-column format… | Done |  | Yes
4.4:66 | 1 | The system shall support positioning of notes at the bottom of the page on which they are being referenced. | Under development |  | Yes
4.4:67 | 1 | The system shall support collecting of notes either at the end of each volume, or at the end of the entire book. | Under development |  | Yes
4.4:68 | 1 | The system shall provide a notes layout fallback mechanism… | To do |  | Yes
4.4:69 | 3 | The system shall support inline rendering of notes right after the note reference… | Under development
4.4:70 | 3 | The system shall support rendering of certain elements such as line numbers in the left margin, taking them out of the normal text flow… | To do
4.4:71 | 3 | The system shall provide the possibility of moving certain content that hinders readability… | To do
4.4:72 | 3 | The system shall provide the possibility of omitting certain content. | To do
4.4:73 | 2 | There shall be the possibility of rendering certain elements such as line numbers in the left margin, not taking them out of the normal text flow… | To do
4.4:74 | 1 | The system shall support single and double line spacing. | Done |  | Yes
4.4:75 | 1 | When printing double-sided with line spacing greater than 1, printed lines shall alternate on odd and even pages. | Done
4.4:76 | 3 | The system shall support line spacing between single and double. | Cancelled
4.5:78 | 1 | The user shall have control over page breaking… | Done |  | Yes
4.5:79 | 3 | The system shall provide the option to disable page breaking… | To do
4.5:80 | 1 | The user shall have control over the page dimensions and the size of page margins. | Done |  | Yes
4.5:81 | 1 | There shall be support for content in the header and footer of pages… | Done |  | Yes
4.5:82 | 1 | The header and footer layout shall be able to change between sections within the document. | Done |  | Yes
4.5:83 | 3 | The system shall support flowing of text into the header or footer… | To do
4.5:84 | 1 | When printing double-sided, there shall be support for hard page breaks that jump to the next right- or left-hand page. | On hold | Tested, decided to omit 'left-hand page' for now | Yes
4.5:85 | 1 | When printing double-sided, the system shall allow the page layout to differ between left- and right-hand pages. | Done |  | Yes
4.5:86 | 3 | Support for mixed braille and ink on the cover page… | To do
4.5:87 | 3 | Support for interlining braille and ink, or combining braille and ink on facing pages… | To do
4.6:88 | 1 | The system shall be able to perform automatic volume breaking… | Under test | To do: advanced volume breaking | Yes
4.6:89 | 1 | The system shall provide the possibility of repeating certain content in several volumes. | Ready for test |  | Yes
4.6:90 | 1 | The system shall support trimming down of a table of contents to a volume-scope table of contents… | Done |  | Yes
4.6:91 | 1 | In the case of an extended table of contents that is not trimmed down, it shall be possible to group entries according to volume… | Under test | Issue fixed and ready for re-test | Yes
4.6:92 | 1 | In the case of endnotes being collected at the end of a book, it shall be possible to group the notes according to volume… | Under development
4.6:93 | 3 | The user shall have some form of manual control over volume breaking. | Planned for sprint 9
4.7:94 | 1 | The system shall support formatting of numbers and other variables in a wide selection of formats… | On hold | Partly implemented
4.7:95 | 2 | The system shall support insertion of content that is not present in the source, through configuration… | To do | Ready for test (smoke test required before acceptance test)
4.7:96 | 1 | The system shall support automatic insertion of content that is not present in the source… | Under development | NLB: done and tested, other: under development | Yes – generated title, colophon and TOC pages for each volume
4.7:97 | 1 | The system shall be able to perform automatic numbering of braille pages and volumes. | On hold | Pages: done and tested, volumes: ready for test | Yes
4.7:98 | 1 | The system shall be able to perform automatic numbering on type ol lists… | To do | Ready for test (smoke test required before acceptance test) | Yes
4.7:99 | 2 | The system shall support resetting of braille page numbering at the start of major sections… | Done
4.7:100 | 3 | The system shall be able to perform automatic numbering of notes… | To do
4.7:101 | 3 | The system shall support resetting braille page numbering for each volume. | To do |  | Yes
4.7:102 | 1 | The system shall be able to evaluate certain variables and counters at so-called fields… | Under test | Needs optimization | Yes
4.7:103 | 1 | The system shall support insertion of certain variables and counters at references evaluated at the target… | To do | Tested implicitly (generated table of content), done | Yes
4.7:104 | 3 | The system shall support insertion of certain variables and counters at referenced items evaluated at the reference… | To do |  | Maybe
4.8:105 | 1 | The system shall provide the possibility of rendering print page breaks as full lines across the width of the page… | On hold | Needs optimization, not implemented for MTM | Yes
4.8:106 | 2 | The system shall provide the possibility of rendering print page breaks as marks in the left margin, taking them out of the normal text flow… | Done |  | Yes
4.8:107 | 2 | The system shall support skipping print page breaks when no text precedes or follows on the same braille page. | On hold |  | Maybe
4.9:108 | 1 | The system shall support templates for different products… | Done |  | Yes
4.9:109 | 1 | The system shall support templates for different end user groups. | Done |  | Yes
4.9:110 | 1 | Users shall be able to reuse templates. | Done |  | Yes
4.9:111 | 1 | Certain users shall be able to create templates. | Done |  | Yes
4.9:112 | 1 | The system shall save jobs so that e.g. a job history can be showed, and jobs can be rerun. | Done |  | Yes
4.9:113 | 1 | The user shall be able to monitor jobs… | Done |  | Yes
4.9:114 | 2 | The system shall provide the user with help and guidance for creating templates. | On hold | Framework for script documentation in place, more actual documentation needed
4.9:115 | 1 | The system shall provide a graphical user interface for creating and monitoring jobs. | To do | Tested implicitly, done | Yes
4.7:117 | 3 | The system shall support the possibility to integrate tactile drawings in braille. | To do
4.7:118 | 3 | The system shall support the creation of symbols lists, when characters have different meaning than normally… | To do
4.10:119 | 3 | The system shall support giving marked up mathematics code in ASCII-Math an output according to the mathematical braille code in the Netherlands. | To do

## MTM
Feature |  |  | State | Comments | Include in acceptance test (+ comments)
3.4:8 |  | The system shall support EPUB 3 as input. | Under development
4.1:25 | 1 | The system shall support editing on block level in order to fix wrong translations… | To do
4.1:26 | 2 | The system shall support editing beyond block level… | To do
4.1:27 | 3 | The system shall be able to merge changes made in the original text with changes made previously in the braille version… | To do
4.1:28 | 3 | The system shall be able to produce synchronization data for various intermediary and output files… | To do
4.1:29 | 3 | The system shall provide a graphical user interface for editing an intermediary braille file. | To do
4.1:30 | 3 | The user interface shall provide a side-by-side view of the original text and braille… | To do
4.1:31 | 3 | There shall be support for inserting braille characters using 6/8 keys on the keyboard. | To do
4.2:32 | 1 | The system shall be able to output various e-braille formats. | Planned for sprint 9
4.2:33 | 1 | The system shall support a new e-braille format. | Planned for sprint 9
4.3:34B | 1 | The system shall be easily extended with new languages - for uncontracted braille… | To do | Not easily testable
4.3:34C | 1 | The system shall support the braille code used in the Netherlands for uncontracted braille. | To do | Under development, see 4.3:34
4.3:34 | 1 | The system shall support the braille code used in Denmark, Finland, Norway, Sweden, Switzerland and the Netherlands for uncontracted braille. | Ready for test | Has been tested a lot implicitly, optimization needed for German (and for emphasis in Dutch: 4.3:38) | YES
4.3:35C | 1 | The system shall support the possibility to leave out capital signs in some products. | Done |  | YES
4.3:35B | 1 | The system shall support the braille code used in the Netherlands for 8-dot braille. | To do | No detailed specifications
4.3:35 | 1 | The system shall support the braille code used in Denmark, Finland, Norway, Sweden and Switzerland for 8-dot braille. | On hold | No detailed specifications
4.3:36 | 2 | The system shall support double letter spacing… | On hold | Needs optimization (wrt hyphenation)
4.3:37B | 1 | The system shall be easily extended with new languages - for contracted braille… | To do | Not easily testable
4.3:37C | 1 | The system shall support the braille code used in the Netherlands for contracted braille. | Cancelled
4.3:37 | 1 | The system shall support the braille code used in Denmark, Norway, Sweden and Switzerland for contracted braille. | Under test | Has been tested a lot implicitly, optimization needed for German
4.3:38 | 1 | The system shall support marking of text-level semantics with braille indicators. | On hold | Under development, new release of Liblouis needed | YES
4.3:39 | 1 | The system shall support marking of visual text styling/typography with braille indicators… | To do | Doesn't seem to be a requirement for anyone after all
4.3:40 | 1 | The system shall have a flexible and configurable mapping from markup to braille indicators… | To do | Ready for test (smoke test required before acceptance test)
4.3:41 | 1 | The system shall be able to perform automatic hyphenation for uncontracted and contracted braille. | On hold | Tested that hyphenation works, but optimization needed for some (workflow has been suggested to improve hyphenation over time, real usage is required for this) | YES, the turning hyphenaton off-feature
4.3:42 | 1 | The system shall support non-standard hyphenation… | Under development
4.3:43 | 2 | When automatic hyphenation is enabled, it shall be possible to exclude certain elements… | To do | Ready for test (smoke test required before acceptance test)
4.3:44 | 1 | The user shall be able to make a top-level configuration… | Under development
4.3:45 | 3 | The user shall have fine-grained control over the translation… | To do | Framework in place, agency-specific code required, no detailed specifications
4.4:46 | 1 | The system shall have support for top, right, bottom and left margins on blocks. | Done
4.4:47 | 1 | The system shall have support for top, right, bottom and left borders and padding on blocks. | Done
4.4:48 | 2 | By default margins shall be collapsing. However there shall be a way to override this behaviour. | On hold
4.4:49 | 2 | By default empty lines at the top and bottom of a page shall be suppressed. However there shall be a way to override this behaviour. | To do | Decided to drop this for now
4.4:50 | 2 | There shall be the possibility of shrinking a block with a border to the size of its contents… | To do | Possibly implement with a OBFL table
4.4:51 | 1 | The system shall have support for first line indentation. | Done |  | YES
4.4:52 | 1 | Besides left-aligned text, the system shall have support for centered and right-aligned text. | Done
4.4:53 | 1 | The system shall support block alignment relative to a vertical position on the page. | Done
4.4:54 | 1 | The system shall by default handle whitespace characters in the source XML according to the following rules… | Ready for test | Ready for acceptance test
4.4:55 | 2 | The user shall be able to override the default handling of whitespace for certain elements… | Ready for test | Ready for acceptance test (except for German: optimization + smoke test needed)
4.4:56 | 2 | The system shall provide a way to control the layout of each table separately. | On hold | Ready for acceptance test (only documentation missing)
4.4:57 | 1 | There shall be the option to reformat a table into a list… | Under test |  | YES, more work is needed for layout of tables in the MTM script. Should be done during week 10.
4.4:58 | 1 | There shall be the option to render a table in matrix format… | Under development |  | YES, more work is needed for layout of tables in the MTM script. Should be done during week 10.
4.4:59 | 2 | When a table in matrix format spans multiple pages, there shall be the possibility of repeating the table heading at the top of each page. | To do | Dotify refactoring required | YES, more work is needed for layout of tables in the MTM script. Should be done during week 10.
4.4:60 | 2 | There shall be the possibility of transposing tables… | To do | Tables as lists: done and tested, matrix tables: to do | YES, more work is needed for layout of tables in the MTM script. Should be done during week 10.
4.4:61 | 2 | The system shall provide a table layout fallback mechanism… | Under development |  | YES, more work is needed for layout of tables in the MTM script. Should be done during week 10.
4.4:62 | 3 | The system shall be able to cope with column- and rowspan in tables… | To do | Tables as lists: done and tested, matrix tables: ready for test | YES, more work is needed for layout of tables in the MTM script. Should be done during week 10.
4.4:63 | 3 | There shall be the option to render a big or complex table in matrix format… | To do
4.4:64 | 3 | There shall be the option to render a wide table on facing pages. | To do
4.4:65 | 1 | The system shall be able to render tables of contents, list of images, index, glossaries, etc. in a two-column format… | Done |  | YES
4.4:66 | 1 | The system shall support positioning of notes at the bottom of the page on which they are being referenced. | Under development |  | YES
4.4:67 | 1 | The system shall support collecting of notes either at the end of each volume, or at the end of the entire book. | Under development |  | YES
4.4:68 | 1 | The system shall provide a notes layout fallback mechanism… | To do
4.4:69 | 3 | The system shall support inline rendering of notes right after the note reference… | Under development
4.4:70 | 3 | The system shall support rendering of certain elements such as line numbers in the left margin, taking them out of the normal text flow… | To do
4.4:71 | 3 | The system shall provide the possibility of moving certain content that hinders readability… | To do
4.4:72 | 3 | The system shall provide the possibility of omitting certain content. | To do
4.4:73 | 2 | There shall be the possibility of rendering certain elements such as line numbers in the left margin, not taking them out of the normal text flow… | To do
4.4:74 | 1 | The system shall support single and double line spacing. | Done |  | YES
4.4:75 | 1 | When printing double-sided with line spacing greater than 1, printed lines shall alternate on odd and even pages. | Done |  | YES
4.4:76 | 3 | The system shall support line spacing between single and double. | Cancelled
4.5:78 | 1 | The user shall have control over page breaking… | Done
4.5:79 | 3 | The system shall provide the option to disable page breaking… | To do
4.5:80 | 1 | The user shall have control over the page dimensions and the size of page margins. | Done |  | YES
4.5:81 | 1 | There shall be support for content in the header and footer of pages… | Done
4.5:82 | 1 | The header and footer layout shall be able to change between sections within the document. | Done
4.5:83 | 3 | The system shall support flowing of text into the header or footer… | To do
4.5:84 | 1 | When printing double-sided, there shall be support for hard page breaks that jump to the next right- or left-hand page. | On hold | Tested, decided to omit 'left-hand page' for now
4.5:85 | 1 | When printing double-sided, the system shall allow the page layout to differ between left- and right-hand pages. | Done
4.5:86 | 3 | Support for mixed braille and ink on the cover page… | To do
4.5:87 | 3 | Support for interlining braille and ink, or combining braille and ink on facing pages… | To do
4.6:88 | 1 | The system shall be able to perform automatic volume breaking… | Under test | To do: advanced volume breaking
4.6:89 | 1 | The system shall provide the possibility of repeating certain content in several volumes. | Ready for test
4.6:90 | 1 | The system shall support trimming down of a table of contents to a volume-scope table of contents… | Done |  | YES
4.6:91 | 1 | In the case of an extended table of contents that is not trimmed down, it shall be possible to group entries according to volume… | Under test | Issue fixed and ready for re-test | YES
4.6:92 | 1 | In the case of endnotes being collected at the end of a book, it shall be possible to group the notes according to volume… | Under development |  | YES
4.6:93 | 3 | The user shall have some form of manual control over volume breaking. | Planned for sprint 9
4.7:94 | 1 | The system shall support formatting of numbers and other variables in a wide selection of formats… | On hold | Partly implemented
4.7:95 | 2 | The system shall support insertion of content that is not present in the source, through configuration… | To do | Ready for test (smoke test required before acceptance test)
4.7:96 | 1 | The system shall support automatic insertion of content that is not present in the source… | Under development | NLB: done and tested, other: under development
4.7:97 | 1 | The system shall be able to perform automatic numbering of braille pages and volumes. | On hold | Pages: done and tested, volumes: ready for test | YES
4.7:98 | 1 | The system shall be able to perform automatic numbering on type ol lists… | To do | Ready for test (smoke test required before acceptance test)
4.7:99 | 2 | The system shall support resetting of braille page numbering at the start of major sections… | Done
4.7:100 | 3 | The system shall be able to perform automatic numbering of notes… | To do
4.7:101 | 3 | The system shall support resetting braille page numbering for each volume. | To do
4.7:102 | 1 | The system shall be able to evaluate certain variables and counters at so-called fields… | Under test | Needs optimization
4.7:103 | 1 | The system shall support insertion of certain variables and counters at references evaluated at the target… | To do | Tested implicitly (generated table of content), done
4.7:104 | 3 | The system shall support insertion of certain variables and counters at referenced items evaluated at the reference… | To do
4.8:105 | 1 | The system shall provide the possibility of rendering print page breaks as full lines across the width of the page… | On hold | Needs optimization, not implemented for MTM | ???? Fråga Joel om detta.
4.8:106 | 2 | The system shall provide the possibility of rendering print page breaks as marks in the left margin, taking them out of the normal text flow… | Done
4.8:107 | 2 | The system shall support skipping print page breaks when no text precedes or follows on the same braille page. | On hold
4.9:108 | 1 | The system shall support templates for different products… | Done |  | YES, we are going to test all reasonable variants that are possible today through the webUI
4.9:109 | 1 | The system shall support templates for different end user groups. | Done
4.9:110 | 1 | Users shall be able to reuse templates. | Done |  | YES
4.9:111 | 1 | Certain users shall be able to create templates. | Done |  | YES
4.9:112 | 1 | The system shall save jobs so that e.g. a job history can be showed, and jobs can be rerun. | Done |  | YES
4.9:113 | 1 | The user shall be able to monitor jobs… | Done |  | YES
4.9:114 | 2 | The system shall provide the user with help and guidance for creating templates. | On hold | Framework for script documentation in place, more actual documentation needed | YES
4.9:115 | 1 | The system shall provide a graphical user interface for creating and monitoring jobs. | To do | Tested implicitly, done
4.7:117 | 3 | The system shall support the possibility to integrate tactile drawings in braille. | To do
4.7:118 | 3 | The system shall support the creation of symbols lists, when characters have different meaning than normally… | To do
4.10:119 | 3 | The system shall support giving marked up mathematics code in ASCII-Math an output according to the mathematical braille code in the Netherlands. | To do

## NLB
Fill in the columns with your name above it. State whether you think the requirement is fulfilled or not by filling out the "go / no go" column, and optionally add comments in the "comments" column.
Test material is available from the Windows share: \\srvdok\Utviklingsavdelingen\Punktskrift\Flernasjonalt punktskriftprosjekt\Acceptance testing\Testmateriale acceptancetesting
[7 empty] | Mats |  | Mari |  | Arne |  | Kari |  | Ammar |  | Jostein
Requirement | Prioritet | Description | Test material / filename | Status | Test comments | Comments from project group | Go / No Go | Comments | Go / No Go | Comments | Go / No Go | Comments | Go / No Go | Comments | Go / No Go | Comments | Go / No Go | Comments
4.3:34 | 1 | The system shall support the braille code used in Denmark, Finland, Norway, Sweden, Switzerland and the Netherlands for uncontracted braille. | Test.DTBook.4.3.34.Norwegian uncontracted braille.xml | Ready for test | Check the signs in the test. | Has been tested a lot implicitly, optimization needed for German (and for emphasis in Dutch: 4.3:38)
4.3:35C | 1 | The system shall support the possibility to leave out capital signs in some products. | Test.DTBook.4.3.35C.Capital sign.xml | Done | Check if it is possible to produce without capital signs, fill in in GUI (Tekstformatering).
4.3:37B | 1 | The system shall be easily extended with new languages - for contracted braille… |  | To do | Jostein/Ammar | Not easily testable
4.3:38 | 1 | The system shall support marking of text-level semantics with braille indicators. | Test.DTBook.4.3.38.text-level semantics with braille indicators.xml | On hold | Check italic and bold, norwegian code in test. | Under development, new release of Liblouis needed
4.3:41 | 1 | The system shall be able to perform automatic hyphenation for uncontracted and contracted braille. | Test.DTBook.4.3.41.Hyphenation.xml | On hold | The test has occational text first, then some spesific words. Do you find the hyphenation good enough? | Tested that hyphenation works, but optimization needed for some (workflow has been suggested to improve hyphenation over time, real usage is required for this)
4.3:44 | 1 | The user shall be able to make a top-level configuration… | Test.DTBook.4.3.44.Top-levelconf(GUI).xml | Under development | Check options in GUI. Are they working? Is somehting missing?
4.4:46 | 1 | The system shall have support for top, right, bottom and left margins on blocks. | Test.DTBook.4.4.51.firstlineintendation.xml | Done | Check that the output have left, right and bottom margins.
4.4:47 | 1 | The system shall have support for top, right, bottom and left borders and padding on blocks. | Test.DTBook.4.4.47.Bordersandpaddingonblocks.xml | Done | Check that <part> and <h1> have borders on blocks.
4.4:51 | 1 | The system shall have support for first line indentation. | Test.DTBook.4.4.51.firstlineintendation.xml | Done | Check 2 intendations in first line in <p>, also in <blockquote>.
4.4:52 | 1 | Besides left-aligned text, the system shall have support for centered and right-aligned text. | Test.DTBook.4.8.106.Originalpagenum.xml | Done | Check braille page number and original page break number, examples of centered and right-aligned text
4.4:53 | 1 | The system shall support block alignment relative to a vertical position on the page. | Test.DTBook.4.4.53.blockalignmentvertical.xml + blockalignmentvertical.css | Done | Check that "Rammetekst" is right-aligned when using the blockalignmentvertical.css
4.4:54 | 1 | The system shall by default handle whitespace characters in the source XML according to the following rules… | Test.DTBook.4.4.54.whitespace | Ready for test | Check that whitespace is removed | Ready for acceptance test
4.4:55 | 2 | The user shall be able to override the default handling of whitespace for certain elements… | Test.DTBook.4.4.55.overridewhitespace.xml + whitespace.css | Ready for test | Check that whitespace remains when tag <pre> is in xml | Ready for acceptance test (except for German: optimization + smoke test needed)
4.4:57 | 1 | There shall be the option to reformat a table into a list… | Test.DTBook.4.4.57.tabletolist.row-by-row.xml | Under test | Check that the table becomes a list, row by row. Semicolon (dot 23) separates columns.
4.4:65 | 1 | The system shall be able to render tables of contents, list of images, index, glossaries, etc. in a two-column format… | Test.DTBook.4.6.89.TOC + nlb-default.9.3.css | Done | Check that TOC is rendered in a two-column format. (Page number is not in separat column) not working 15.3
4.4:66 | 1 | The system shall support positioning of notes at the bottom of the page on which they are being referenced. | Test.DTBook.4.4.66.smallnotes.xml + footnotes.css | Under development | Check that Noteref no. 1 on orig.p.148 is placed in bottom of page (haging indent). Noteref on a row of its own for easy retrieval (dot 6 as notemark). Do we need a border before footnote to find it easier?
4.4:67 | 1 | The system shall support collecting of notes either at the end of each volume, or at the end of the entire book. | Test.DTBook.4.4.67.notes.xml + volumeendnotes.css | Under development | Check that noteref no. 1 on orig.p. 148 is placed in end of volume. Check that other notes are placed in end of volume as well.
4.4:68 | 1 | The system shall provide a notes layout fallback mechanism… | Test.DTBook.notesfallback.xml + notesfallback.css | To do | The rules goes like this: 1. If all notes in book is halv a page or less, they are placed as footnoes. 2. If some of the notes are larger than halv a page, all notes are put in the end of volume. In the example, note 4 (orig.p.205) is more than halv a page, therefore all notes in the book is set as endnotes placed last in each volume.
4.4:74 | 1 | The system shall support single and double line spacing. | Test.DTBook.4.8.106.Originalpagenum.xml | Done | Check that double line spacing works. (Under Tekstformatering in GUI)
4.4:75 | 1 | When printing double-sided with line spacing greater than 1, printed lines shall alternate on odd and even pages. | Test.DTBook.4.8.106.Originalpagenum.xml | Done | Check that print lines alternate.
4.5:78 | 1 | The user shall have control over page breaking… | Test.DTBook.4.5.78.orphanwidow.xml + orphan2.css | Done | Mari: test this toghether with Ammar! Mats can skip this one
4.5:80 | 1 | The user shall have control over the page dimensions and the size of page margins. | Test.DTBook.4.5.80.pagedimensions.xml | Done | Adjust pagelayout in GUI (Layout).
4.5:81 | 1 | There shall be support for content in the header and footer of pages… | Test.DTBook.4.8.106.Originalpagenum.xml | Done | Check content in footer, braille page number (center) and print page number (right). More content in header/footer possible with adjustments in CSS.
4.5:84 | 1 | When printing double-sided, there shall be support for hard page breaks that jump to the next right- or left-hand page. | Test.DTBook.4.5.84.hardpagebreaks.xml | On hold | h1 shall start on a new right page. Not working 15.3 | Tested, decided to omit 'left-hand page' for now
4.5:85 | 1 | When printing double-sided, the system shall allow the page layout to differ between left- and right-hand pages. | Test.DTBook.4.5.85.differinglayoutleftright.xml + differinglayoutleftright.css | Done | Check that footer differ on left and right page.
4.6:88 | 1 | The system shall be able to perform automatic volume breaking… | Test.DTBook.4.6.88.Volumebreaking.simple.xml | Under test | Check that the file is divided into volumes. By now just simple volume breaking without rules. | To do: advanced volume breaking
4.6:89 | 1 | The system shall provide the possibility of repeating certain content in several volumes. | Test.DTBook.4.6.88.Volumebreaking.simple.xml | Ready for test | Repeating titlepage.
4.6:90 | 1 | The system shall support trimming down of a table of contents to a volume-scope table of contents… | Test.DTBook.4.6.89.TOC + nlb-default.9.3.css | Done | Note: In GUI Generert innhold: Dybde på innholdsfortegnelse must be more than 0 for TOC to be generated (1=h1, 2=h2). Check that TOC for each volume is genereated. Check that TOC for the whole book is in start of volume 1. Placement and layout is not quite finished)
4.7:96 | 1 | The system shall support automatic insertion of content that is not present in the source… | Test.DTBook.4.7.102.certainvariablesandcounters.xml | Under development | Check that "Om boka" is present | NLB: done and tested, other: under development
4.7:97 | 1 | The system shall be able to perform automatic numbering of braille pages and volumes. | Test.DTBook.4.6.88.Volumebreaking.simple.xml | On hold | Check that automatic numbering of braille pages works (automatic numbering of volumes is not ready) | Pages: done and tested, volumes: ready for test
4.7:98 | 1 | The system shall be able to perform automatic numbering on type ol lists… | Test.DTBook.4.6.98.NumberingLists.xml* | To do | Implemented? Not working 15.3 | Ready for test (smoke test required before acceptance test)
4.7:102 | 1 | The system shall be able to evaluate certain variables and counters at so-called fields… | Test.DTBook.4.6.88.Volumebreaking.simple.xml | Under test | Check that volume x of y works (not working yet) | Needs optimization
4.8:106 | 2 | The system shall provide the possibility of rendering print page breaks as marks in the left margin, taking them out of the normal text flow… | Test.DTBook.4.8.106.Originalpagenum.xml | Done | Check that a full cell (123456) is present in the left margin at original page break
4.9:108 | 1 | The system shall support templates for different products… | Test.DTBook.4.9.108.templates.xml + tidsskrift.css https://github.com/daisy/pipeline-webui/wiki/Templating | Done | Try NLBs template for periodicals ("Tidsskrifter"), and see that the result becomes different than if you convert the same book without using the template.
4.9:109 | 1 | The system shall support templates for different end user groups. | https://github.com/daisy/pipeline-webui/wiki/Templating | Done | Can be skipped. Tested implicitly by 4.9:108.
4.9:110 | 1 | Users shall be able to reuse templates. | https://github.com/daisy/pipeline-webui/wiki/Templating | Done | Can be skipped. Tested implicitly by 4.9:108
4.9:111 | 1 | Certain users shall be able to create templates. | https://github.com/daisy/pipeline-webui/wiki/Templating | Done | Try following the instructions in the "Templating" user guide to create a template.
4.9:112 | 1 | The system shall save jobs so that e.g. a job history can be showed, and jobs can be rerun. | https://github.com/daisy/pipeline-webui/wiki/User-Guide | Done | Check the "jobs" view to see if your previous jobs are visible and that you can click them to see more details and download results.
4.9:113 | 1 | The user shall be able to monitor jobs… | https://github.com/daisy/pipeline-webui/wiki/User-Guide | Done | Check that jobs are in a "running" state when they are running, and that messages are being output to the job view page while the job is running. Also see thta when a job is running, it will be "running" in the jobs listing as well.
4.9:114 | 2 | The system shall provide the user with help and guidance for creating templates. | https://github.com/daisy/pipeline-webui/wiki/Templating | On hold | This is where you find documentation for templating. | Framework for script documentation in place, more actual documentation needed
We do not consider the following requirements during this acceptance test. They are listed here for completeness sake, but do not need to be tested:
3.4:8 |  | The system shall support EPUB 3 as input. |  | Under development
4.1:25 | 1 | The system shall support editing on block level in order to fix wrong translations… |  | To do
4.1:26 | 2 | The system shall support editing beyond block level… |  | To do
4.1:27 | 3 | The system shall be able to merge changes made in the original text with changes made previously in the braille version… |  | To do
4.1:28 | 3 | The system shall be able to produce synchronization data for various intermediary and output files… |  | To do
4.1:29 | 3 | The system shall provide a graphical user interface for editing an intermediary braille file. |  | To do
4.1:30 | 3 | The user interface shall provide a side-by-side view of the original text and braille… |  | To do
4.1:31 | 3 | There shall be support for inserting braille characters using 6/8 keys on the keyboard. |  | To do
4.2:32 | 1 | The system shall be able to output various e-braille formats. |  | Planned for sprint 9
4.2:33 | 1 | The system shall support a new e-braille format. |  | Planned for sprint 9
4.3:34B | 1 | The system shall be easily extended with new languages - for uncontracted braille… |  | To do |  | Not easily testable
4.3:35 | 1 | The system shall support the braille code used in Denmark, Finland, Norway, Sweden and Switzerland for 8-dot braille. |  | On hold |  | No detailed specifications
4.3:36 | 2 | The system shall support double letter spacing… |  | On hold |  | Needs optimization (wrt hyphenation)
4.3:37 | 1 | The system shall support the braille code used in Denmark, Norway, Sweden and Switzerland for contracted braille. |  | Under test |  | Has been tested a lot implicitly, optimization needed for German
4.3:39 | 1 | The system shall support marking of visual text styling/typography with braille indicators… |  | To do |  | Doesn't seem to be a requirement for anyone after all
4.3:40 | 1 | The system shall have a flexible and configurable mapping from markup to braille indicators… |  | To do |  | Ready for test (smoke test required before acceptance test)
4.3:42 | 1 | The system shall support non-standard hyphenation… |  | Under development
4.3:43 | 2 | When automatic hyphenation is enabled, it shall be possible to exclude certain elements… |  | To do |  | Ready for test (smoke test required before acceptance test)
4.3:45 | 3 | The user shall have fine-grained control over the translation… |  | To do |  | Framework in place, agency-specific code required, no detailed specifications
4.4:48 | 2 | By default margins shall be collapsing. However there shall be a way to override this behaviour. |  | On hold
4.4:49 | 2 | By default empty lines at the top and bottom of a page shall be suppressed. However there shall be a way to override this behaviour. |  | To do |  | Decided to drop this for now
4.4:50 | 2 | There shall be the possibility of shrinking a block with a border to the size of its contents… |  | To do |  | Possibly implement with a OBFL table
4.4:56 | 2 | The system shall provide a way to control the layout of each table separately. |  | On hold |  | Ready for acceptance test (only documentation missing)
4.4:58 | 1 | There shall be the option to render a table in matrix format… |  | Under development
4.4:59 | 2 | When a table in matrix format spans multiple pages, there shall be the possibility of repeating the table heading at the top of each page. |  | To do |  | Dotify refactoring required
4.4:60 | 2 | There shall be the possibility of transposing tables… |  | To do |  | Tables as lists: done and tested, matrix tables: to do
4.4:61 | 2 | The system shall provide a table layout fallback mechanism… |  | Under development
4.4:62 | 3 | The system shall be able to cope with column- and rowspan in tables… |  | To do |  | Tables as lists: done and tested, matrix tables: ready for test
4.4:63 | 3 | There shall be the option to render a big or complex table in matrix format… |  | To do
4.4:64 | 3 | There shall be the option to render a wide table on facing pages. |  | To do
4.4:69 | 3 | The system shall support inline rendering of notes right after the note reference… |  | Under development
4.4:70 | 3 | The system shall support rendering of certain elements such as line numbers in the left margin, taking them out of the normal text flow… |  | To do
4.4:71 | 3 | The system shall provide the possibility of moving certain content that hinders readability… |  | To do
4.4:72 | 3 | The system shall provide the possibility of omitting certain content. |  | To do
4.4:73 | 2 | There shall be the possibility of rendering certain elements such as line numbers in the left margin, not taking them out of the normal text flow… |  | To do
4.4:76 | 3 | The system shall support line spacing between single and double. |  | Cancelled
4.5:79 | 3 | The system shall provide the option to disable page breaking… |  | To do
4.5:82 | 1 | The header and footer layout shall be able to change between sections within the document. |  | Done
4.5:83 | 3 | The system shall support flowing of text into the header or footer… |  | To do
4.5:86 | 3 | Support for mixed braille and ink on the cover page… |  | To do
4.5:87 | 3 | Support for interlining braille and ink, or combining braille and ink on facing pages… |  | To do
4.6:91 | 1 | In the case of an extended table of contents that is not trimmed down, it shall be possible to group entries according to volume… |  | Under test |  | Issue fixed and ready for re-test
4.6:92 | 1 | In the case of endnotes being collected at the end of a book, it shall be possible to group the notes according to volume… |  | Under development
4.6:93 | 3 | The user shall have some form of manual control over volume breaking. |  | Planned for sprint 9
4.7:94 | 1 | The system shall support formatting of numbers and other variables in a wide selection of formats… |  | On hold |  | Partly implemented
4.7:95 | 2 | The system shall support insertion of content that is not present in the source, through configuration… |  | To do |  | Ready for test (smoke test required before acceptance test)
4.7:99 | 2 | The system shall support resetting of braille page numbering at the start of major sections… |  | Done
4.7:100 | 3 | The system shall be able to perform automatic numbering of notes… |  | To do
4.7:101 | 3 | The system shall support resetting braille page numbering for each volume. |  | To do
4.7:103 | 1 | The system shall support insertion of certain variables and counters at references evaluated at the target… |  | To do |  | Tested implicitly (generated table of content), done
4.7:104 | 3 | The system shall support insertion of certain variables and counters at referenced items evaluated at the reference… |  | To do
4.8:105 | 1 | The system shall provide the possibility of rendering print page breaks as full lines across the width of the page… |  | On hold |  | Needs optimization, not implemented for MTM
4.8:107 | 2 | The system shall support skipping print page breaks when no text precedes or follows on the same braille page. |  | On hold
4.9:115 | 1 | The system shall provide a graphical user interface for creating and monitoring jobs. |  | To do |  | Tested implicitly, done
4.7:117 | 3 | The system shall support the possibility to integrate tactile drawings in braille. |  | To do
4.7:118 | 3 | The system shall support the creation of symbols lists, when characters have different meaning than normally… |  | To do
4.10:119 | 3 | The system shall support giving marked up mathematics code in ASCII-Math an output according to the mathematical braille code in the Netherlands. |  | To do

## SBS
Feature |  |  | State | Comments | Include in acceptance test (+ comments)
3.4:8 |  | The system shall support EPUB 3 as input. | Under development |  | no
4.1:25 | 1 | The system shall support editing on block level in order to fix wrong translations… | To do |  | no
4.1:26 | 2 | The system shall support editing beyond block level… | To do |  | no
4.1:27 | 3 | The system shall be able to merge changes made in the original text with changes made previously in the braille version… | To do |  | no
4.1:28 | 3 | The system shall be able to produce synchronization data for various intermediary and output files… | To do |  | no
4.1:29 | 3 | The system shall provide a graphical user interface for editing an intermediary braille file. | To do |  | no
4.1:30 | 3 | The user interface shall provide a side-by-side view of the original text and braille… | To do |  | no
4.1:31 | 3 | There shall be support for inserting braille characters using 6/8 keys on the keyboard. | To do |  | no
4.2:32 | 1 | The system shall be able to output various e-braille formats. | Planned for sprint 9 |  | no
4.2:33 | 1 | The system shall support a new e-braille format. | Planned for sprint 9 |  | no
4.3:34B | 1 | The system shall be easily extended with new languages - for uncontracted braille… | To do | Not easily testable | no
4.3:34C | 1 | The system shall support the braille code used in the Netherlands for uncontracted braille. | To do | Under development, see 4.3:34 | no
4.3:34 | 1 | The system shall support the braille code used in Denmark, Finland, Norway, Sweden, Switzerland and the Netherlands for uncontracted braille. | Ready for test | Has been tested a lot implicitly, optimization needed for German (and for emphasis in Dutch: 4.3:38) | yes
4.3:35C | 1 | The system shall support the possibility to leave out capital signs in some products. | Done |  | no
4.3:35B | 1 | The system shall support the braille code used in the Netherlands for 8-dot braille. | To do | No detailed specifications | no
4.3:35 | 1 | The system shall support the braille code used in Denmark, Finland, Norway, Sweden and Switzerland for 8-dot braille. | On hold | No detailed specifications | no
4.3:36 | 2 | The system shall support double letter spacing… | On hold | Needs optimization (wrt hyphenation) | no
4.3:37B | 1 | The system shall be easily extended with new languages - for contracted braille… | To do | Not easily testable | no
4.3:37C | 1 | The system shall support the braille code used in the Netherlands for contracted braille. | Cancelled |  | no
4.3:37 | 1 | The system shall support the braille code used in Denmark, Norway, Sweden and Switzerland for contracted braille. | Under test | Has been tested a lot implicitly, optimization needed for German | no
4.3:38 | 1 | The system shall support marking of text-level semantics with braille indicators. | On hold | Under development, new release of Liblouis needed | yes
4.3:39 | 1 | The system shall support marking of visual text styling/typography with braille indicators… | To do | Doesn't seem to be a requirement for anyone after all | no
4.3:40 | 1 | The system shall have a flexible and configurable mapping from markup to braille indicators… | To do | Ready for test (smoke test required before acceptance test) | no
4.3:41 | 1 | The system shall be able to perform automatic hyphenation for uncontracted and contracted braille. | On hold | Tested that hyphenation works, but optimization needed for some (workflow has been suggested to improve hyphenation over time, real usage is required for this) | yes
4.3:42 | 1 | The system shall support non-standard hyphenation… | Under development |  | no
4.3:43 | 2 | When automatic hyphenation is enabled, it shall be possible to exclude certain elements… | To do | Ready for test (smoke test required before acceptance test) | yes
4.3:44 | 1 | The user shall be able to make a top-level configuration… | Under development |  | yes
4.3:45 | 3 | The user shall have fine-grained control over the translation… | To do | Framework in place, agency-specific code required, no detailed specifications | yes
4.4:46 | 1 | The system shall have support for top, right, bottom and left margins on blocks. | Done |  | yes
4.4:47 | 1 | The system shall have support for top, right, bottom and left borders and padding on blocks. | Done |  | yes
4.4:48 | 2 | By default margins shall be collapsing. However there shall be a way to override this behaviour. | On hold |  | yes
4.4:49 | 2 | By default empty lines at the top and bottom of a page shall be suppressed. However there shall be a way to override this behaviour. | To do | Decided to drop this for now | yes
4.4:50 | 2 | There shall be the possibility of shrinking a block with a border to the size of its contents… | To do | Possibly implement with a OBFL table | yes
4.4:51 | 1 | The system shall have support for first line indentation. | Done |  | yes
4.4:52 | 1 | Besides left-aligned text, the system shall have support for centered and right-aligned text. | Done |  | yes
4.4:53 | 1 | The system shall support block alignment relative to a vertical position on the page. | Done |  | yes
4.4:54 | 1 | The system shall by default handle whitespace characters in the source XML according to the following rules… | Ready for test | Ready for acceptance test | yes
4.4:55 | 2 | The user shall be able to override the default handling of whitespace for certain elements… | Ready for test | Ready for acceptance test (except for German: optimization + smoke test needed) | no
4.4:56 | 2 | The system shall provide a way to control the layout of each table separately. | On hold | Ready for acceptance test (only documentation missing) | yes
4.4:57 | 1 | There shall be the option to reformat a table into a list… | Under test |  | yes
4.4:58 | 1 | There shall be the option to render a table in matrix format… | Under development |  | yes
4.4:59 | 2 | When a table in matrix format spans multiple pages, there shall be the possibility of repeating the table heading at the top of each page. | To do | Dotify refactoring required | yes
4.4:60 | 2 | There shall be the possibility of transposing tables… | To do | Tables as lists: done and tested, matrix tables: to do | yes
4.4:61 | 2 | The system shall provide a table layout fallback mechanism… | Under development |  | no
4.4:62 | 3 | The system shall be able to cope with column- and rowspan in tables… | To do | Tables as lists: done and tested, matrix tables: ready for test | yes
4.4:63 | 3 | There shall be the option to render a big or complex table in matrix format… | To do |  | no
4.4:64 | 3 | There shall be the option to render a wide table on facing pages. | To do |  | no
4.4:65 | 1 | The system shall be able to render tables of contents, list of images, index, glossaries, etc. in a two-column format… | Done |  | yes
4.4:66 | 1 | The system shall support positioning of notes at the bottom of the page on which they are being referenced. | Under development |  | yes
4.4:67 | 1 | The system shall support collecting of notes either at the end of each volume, or at the end of the entire book. | Under development |  | yes
4.4:68 | 1 | The system shall provide a notes layout fallback mechanism… | To do |  | no
4.4:69 | 3 | The system shall support inline rendering of notes right after the note reference… | Under development |  | no
4.4:70 | 3 | The system shall support rendering of certain elements such as line numbers in the left margin, taking them out of the normal text flow… | To do |  | yes
4.4:71 | 3 | The system shall provide the possibility of moving certain content that hinders readability… | To do |  | no
4.4:72 | 3 | The system shall provide the possibility of omitting certain content. | To do |  | yes
4.4:73 | 2 | There shall be the possibility of rendering certain elements such as line numbers in the left margin, not taking them out of the normal text flow… | To do |  | yes
4.4:74 | 1 | The system shall support single and double line spacing. | Done |  | yes
4.4:75 | 1 | When printing double-sided with line spacing greater than 1, printed lines shall alternate on odd and even pages. | Done |  | yes
4.4:76 | 3 | The system shall support line spacing between single and double. | Cancelled |  | no
4.5:78 | 1 | The user shall have control over page breaking… | Done |  | yes
4.5:79 | 3 | The system shall provide the option to disable page breaking… | To do |  | yes
4.5:80 | 1 | The user shall have control over the page dimensions and the size of page margins. | Done |  | yes
4.5:81 | 1 | There shall be support for content in the header and footer of pages… | Done |  | yes
4.5:82 | 1 | The header and footer layout shall be able to change between sections within the document. | Done |  | yes
4.5:83 | 3 | The system shall support flowing of text into the header or footer… | To do |  | yes
4.5:84 | 1 | When printing double-sided, there shall be support for hard page breaks that jump to the next right- or left-hand page. | On hold | Tested, decided to omit 'left-hand page' for now | yes
4.5:85 | 1 | When printing double-sided, the system shall allow the page layout to differ between left- and right-hand pages. | Done |  | yes
4.5:86 | 3 | Support for mixed braille and ink on the cover page… | To do |  | no
4.5:87 | 3 | Support for interlining braille and ink, or combining braille and ink on facing pages… | To do |  | no
4.6:88 | 1 | The system shall be able to perform automatic volume breaking… | Under test | To do: advanced volume breaking | no
4.6:89 | 1 | The system shall provide the possibility of repeating certain content in several volumes. | Ready for test |  | yes
4.6:90 | 1 | The system shall support trimming down of a table of contents to a volume-scope table of contents… | Done |  | yes
4.6:91 | 1 | In the case of an extended table of contents that is not trimmed down, it shall be possible to group entries according to volume… | Under test | Issue fixed and ready for re-test | no
4.6:92 | 1 | In the case of endnotes being collected at the end of a book, it shall be possible to group the notes according to volume… | Under development |  | yes
4.6:93 | 3 | The user shall have some form of manual control over volume breaking. | Planned for sprint 9 |  | yes
4.7:94 | 1 | The system shall support formatting of numbers and other variables in a wide selection of formats… | On hold | Partly implemented | yes
4.7:95 | 2 | The system shall support insertion of content that is not present in the source, through configuration… | To do | Ready for test (smoke test required before acceptance test) | yes
4.7:96 | 1 | The system shall support automatic insertion of content that is not present in the source… | Under development | NLB: done and tested, other: under development | yes
4.7:97 | 1 | The system shall be able to perform automatic numbering of braille pages and volumes. | On hold | Pages: done and tested, volumes: ready for test | yes
4.7:98 | 1 | The system shall be able to perform automatic numbering on type ol lists… | To do | Ready for test (smoke test required before acceptance test) | yes
4.7:99 | 2 | The system shall support resetting of braille page numbering at the start of major sections… | Done |  | yes
4.7:100 | 3 | The system shall be able to perform automatic numbering of notes… | To do |  | yes
4.7:101 | 3 | The system shall support resetting braille page numbering for each volume. | To do |  | no
4.7:102 | 1 | The system shall be able to evaluate certain variables and counters at so-called fields… | Under test | Needs optimization | yes
4.7:103 | 1 | The system shall support insertion of certain variables and counters at references evaluated at the target… | To do | Tested implicitly (generated table of content), done | yes
4.7:104 | 3 | The system shall support insertion of certain variables and counters at referenced items evaluated at the reference… | To do |  | yes
4.8:105 | 1 | The system shall provide the possibility of rendering print page breaks as full lines across the width of the page… | On hold | Needs optimization, not implemented for MTM | no
4.8:106 | 2 | The system shall provide the possibility of rendering print page breaks as marks in the left margin, taking them out of the normal text flow… | Done |  | no
4.8:107 | 2 | The system shall support skipping print page breaks when no text precedes or follows on the same braille page. | On hold |  | no
4.9:108 | 1 | The system shall support templates for different products… | Done |  | yes
4.9:109 | 1 | The system shall support templates for different end user groups. | Done |  | no
4.9:110 | 1 | Users shall be able to reuse templates. | Done |  | yes
4.9:111 | 1 | Certain users shall be able to create templates. | Done |  | no
4.9:112 | 1 | The system shall save jobs so that e.g. a job history can be showed, and jobs can be rerun. | Done |  | no
4.9:113 | 1 | The user shall be able to monitor jobs… | Done |  | no
4.9:114 | 2 | The system shall provide the user with help and guidance for creating templates. | On hold | Framework for script documentation in place, more actual documentation needed | no
4.9:115 | 1 | The system shall provide a graphical user interface for creating and monitoring jobs. | To do | Tested implicitly, done | yes
4.7:117 | 3 | The system shall support the possibility to integrate tactile drawings in braille. | To do |  | no
4.7:118 | 3 | The system shall support the creation of symbols lists, when characters have different meaning than normally… | To do |  | yes
4.10:119 | 3 | The system shall support giving marked up mathematics code in ASCII-Math an output according to the mathematical braille code in the Netherlands. | To do |  | no