## Sheet 1
Feature |  |  | State | Comments | Include in acceptance test (+ comments)
3.4:8 |  | The system shall support EPUB 3 as input. | Under development |  | Yes
4.1:25 | 1 | The system shall support editing on block level in order to fix wrong translations… | To do
4.1:26 | 2 | The system shall support editing beyond block level… | To do
4.1:27 | 3 | The system shall be able to merge changes made in the original text with changes made previously in the braille version… | To do
4.1:28 | 3 | The system shall be able to produce synchronization data for various intermediary and output files… | To do
4.1:29 | 3 | The system shall provide a graphical user interface for editing an intermediary braille file. | To do
4.1:30 | 3 | The user interface shall provide a side-by-side view of the original text and braille… | To do
4.1:31 | 3 | There shall be support for inserting braille characters using 6/8 keys on the keyboard. | To do
4.2:32 | 1 | The system shall be able to output various e-braille formats. | Planned for sprint 9
4.2:33 | 1 | The system shall support a new e-braille format. | Planned for sprint 9
4.3:34B | 1 | The system shall be easily extended with new languages - for uncontracted braille… | To do | Not easily testable
4.3:34C | 1 | The system shall support the braille code used in the Netherlands for uncontracted braille. | To do | Under development, see 4.3:34
4.3:34 | 1 | The system shall support the braille code used in Denmark, Finland, Norway, Sweden, Switzerland and the Netherlands for uncontracted braille. | Ready for test | Has been tested a lot implicitly, optimization needed for German (and for emphasis in Dutch: 4.3:38) | Yes
4.3:35C | 1 | The system shall support the possibility to leave out capital signs in some products. | Done
4.3:35B | 1 | The system shall support the braille code used in the Netherlands for 8-dot braille. | To do | No detailed specifications
4.3:35 | 1 | The system shall support the braille code used in Denmark, Finland, Norway, Sweden and Switzerland for 8-dot braille. | On hold | No detailed specifications
4.3:36 | 2 | The system shall support double letter spacing… | On hold | Needs optimization (wrt hyphenation)
4.3:37B | 1 | The system shall be easily extended with new languages - for contracted braille… | To do | Not easily testable
4.3:37C | 1 | The system shall support the braille code used in the Netherlands for contracted braille. | Cancelled
4.3:37 | 1 | The system shall support the braille code used in Denmark, Norway, Sweden and Switzerland for contracted braille. | Under test | Has been tested a lot implicitly, optimization needed for German | Yes
4.3:38 | 1 | The system shall support marking of text-level semantics with braille indicators. | On hold | Under development, new release of Liblouis needed | Yes – certainly needs testing at some point, even if it can't be done just now
4.3:39 | 1 | The system shall support marking of visual text styling/typography with braille indicators… | To do | Doesn't seem to be a requirement for anyone after all
4.3:40 | 1 | The system shall have a flexible and configurable mapping from markup to braille indicators… | To do | Ready for test (smoke test required before acceptance test) | Yes
4.3:41 | 1 | The system shall be able to perform automatic hyphenation for uncontracted and contracted braille. | On hold | Tested that hyphenation works, but optimization needed for some (workflow has been suggested to improve hyphenation over time, real usage is required for this) | Yes
4.3:42 | 1 | The system shall support non-standard hyphenation… | Under development
4.3:43 | 2 | When automatic hyphenation is enabled, it shall be possible to exclude certain elements… | To do | Ready for test (smoke test required before acceptance test)
4.3:44 | 1 | The user shall be able to make a top-level configuration… | Under development |  | Yes
4.3:45 | 3 | The user shall have fine-grained control over the translation… | To do | Framework in place, agency-specific code required, no detailed specifications
4.4:46 | 1 | The system shall have support for top, right, bottom and left margins on blocks. | Done |  | Yes
4.4:47 | 1 | The system shall have support for top, right, bottom and left borders and padding on blocks. | Done |  | Yes – padding only
4.4:48 | 2 | By default margins shall be collapsing. However there shall be a way to override this behaviour. | On hold
4.4:49 | 2 | By default empty lines at the top and bottom of a page shall be suppressed. However there shall be a way to override this behaviour. | To do | Decided to drop this for now
4.4:50 | 2 | There shall be the possibility of shrinking a block with a border to the size of its contents… | To do | Possibly implement with a OBFL table
4.4:51 | 1 | The system shall have support for first line indentation. | Done |  | Yes
4.4:52 | 1 | Besides left-aligned text, the system shall have support for centered and right-aligned text. | Done |  | Yes
4.4:53 | 1 | The system shall support block alignment relative to a vertical position on the page. | Done |  | Yes
4.4:54 | 1 | The system shall by default handle whitespace characters in the source XML according to the following rules… | Ready for test | Ready for acceptance test | Yes
4.4:55 | 2 | The user shall be able to override the default handling of whitespace for certain elements… | Ready for test | Ready for acceptance test (except for German: optimization + smoke test needed) | Yes
4.4:56 | 2 | The system shall provide a way to control the layout of each table separately. | On hold | Ready for acceptance test (only documentation missing) | Yes
4.4:57 | 1 | There shall be the option to reformat a table into a list… | Under test |  | Yes
4.4:58 | 1 | There shall be the option to render a table in matrix format… | Under development
4.4:59 | 2 | When a table in matrix format spans multiple pages, there shall be the possibility of repeating the table heading at the top of each page. | To do | Dotify refactoring required
4.4:60 | 2 | There shall be the possibility of transposing tables… | To do | Tables as lists: done and tested, matrix tables: to do | Yes
4.4:61 | 2 | The system shall provide a table layout fallback mechanism… | Under development
4.4:62 | 3 | The system shall be able to cope with column- and rowspan in tables… | To do | Tables as lists: done and tested, matrix tables: ready for test | Yes
4.4:63 | 3 | There shall be the option to render a big or complex table in matrix format… | To do
4.4:64 | 3 | There shall be the option to render a wide table on facing pages. | To do
4.4:65 | 1 | The system shall be able to render tables of contents, list of images, index, glossaries, etc. in a two-column format… | Done |  | Yes
4.4:66 | 1 | The system shall support positioning of notes at the bottom of the page on which they are being referenced. | Under development |  | Yes
4.4:67 | 1 | The system shall support collecting of notes either at the end of each volume, or at the end of the entire book. | Under development |  | Yes
4.4:68 | 1 | The system shall provide a notes layout fallback mechanism… | To do |  | Yes
4.4:69 | 3 | The system shall support inline rendering of notes right after the note reference… | Under development
4.4:70 | 3 | The system shall support rendering of certain elements such as line numbers in the left margin, taking them out of the normal text flow… | To do
4.4:71 | 3 | The system shall provide the possibility of moving certain content that hinders readability… | To do
4.4:72 | 3 | The system shall provide the possibility of omitting certain content. | To do
4.4:73 | 2 | There shall be the possibility of rendering certain elements such as line numbers in the left margin, not taking them out of the normal text flow… | To do
4.4:74 | 1 | The system shall support single and double line spacing. | Done |  | Yes
4.4:75 | 1 | When printing double-sided with line spacing greater than 1, printed lines shall alternate on odd and even pages. | Done
4.4:76 | 3 | The system shall support line spacing between single and double. | Cancelled
4.5:78 | 1 | The user shall have control over page breaking… | Done |  | Yes
4.5:79 | 3 | The system shall provide the option to disable page breaking… | To do
4.5:80 | 1 | The user shall have control over the page dimensions and the size of page margins. | Done |  | Yes
4.5:81 | 1 | There shall be support for content in the header and footer of pages… | Done |  | Yes
4.5:82 | 1 | The header and footer layout shall be able to change between sections within the document. | Done |  | Yes
4.5:83 | 3 | The system shall support flowing of text into the header or footer… | To do
4.5:84 | 1 | When printing double-sided, there shall be support for hard page breaks that jump to the next right- or left-hand page. | On hold | Tested, decided to omit 'left-hand page' for now | Yes
4.5:85 | 1 | When printing double-sided, the system shall allow the page layout to differ between left- and right-hand pages. | Done |  | Yes
4.5:86 | 3 | Support for mixed braille and ink on the cover page… | To do
4.5:87 | 3 | Support for interlining braille and ink, or combining braille and ink on facing pages… | To do
4.6:88 | 1 | The system shall be able to perform automatic volume breaking… | Under test | To do: advanced volume breaking | Yes
4.6:89 | 1 | The system shall provide the possibility of repeating certain content in several volumes. | Ready for test |  | Yes
4.6:90 | 1 | The system shall support trimming down of a table of contents to a volume-scope table of contents… | Done |  | Yes
4.6:91 | 1 | In the case of an extended table of contents that is not trimmed down, it shall be possible to group entries according to volume… | Under test | Issue fixed and ready for re-test | Yes
4.6:92 | 1 | In the case of endnotes being collected at the end of a book, it shall be possible to group the notes according to volume… | Under development
4.6:93 | 3 | The user shall have some form of manual control over volume breaking. | Planned for sprint 9
4.7:94 | 1 | The system shall support formatting of numbers and other variables in a wide selection of formats… | On hold | Partly implemented
4.7:95 | 2 | The system shall support insertion of content that is not present in the source, through configuration… | To do | Ready for test (smoke test required before acceptance test)
4.7:96 | 1 | The system shall support automatic insertion of content that is not present in the source… | Under development | NLB: done and tested, other: under development | Yes – generated title, colophon and TOC pages for each volume
4.7:97 | 1 | The system shall be able to perform automatic numbering of braille pages and volumes. | On hold | Pages: done and tested, volumes: ready for test | Yes
4.7:98 | 1 | The system shall be able to perform automatic numbering on type ol lists… | To do | Ready for test (smoke test required before acceptance test) | Yes
4.7:99 | 2 | The system shall support resetting of braille page numbering at the start of major sections… | Done
4.7:100 | 3 | The system shall be able to perform automatic numbering of notes… | To do
4.7:101 | 3 | The system shall support resetting braille page numbering for each volume. | To do |  | Yes
4.7:102 | 1 | The system shall be able to evaluate certain variables and counters at so-called fields… | Under test | Needs optimization | Yes
4.7:103 | 1 | The system shall support insertion of certain variables and counters at references evaluated at the target… | To do | Tested implicitly (generated table of content), done | Yes
4.7:104 | 3 | The system shall support insertion of certain variables and counters at referenced items evaluated at the reference… | To do |  | Maybe
4.8:105 | 1 | The system shall provide the possibility of rendering print page breaks as full lines across the width of the page… | On hold | Needs optimization, not implemented for MTM | Yes
4.8:106 | 2 | The system shall provide the possibility of rendering print page breaks as marks in the left margin, taking them out of the normal text flow… | Done |  | Yes
4.8:107 | 2 | The system shall support skipping print page breaks when no text precedes or follows on the same braille page. | On hold |  | Maybe
4.9:108 | 1 | The system shall support templates for different products… | Done |  | Yes
4.9:109 | 1 | The system shall support templates for different end user groups. | Done |  | Yes
4.9:110 | 1 | Users shall be able to reuse templates. | Done |  | Yes
4.9:111 | 1 | Certain users shall be able to create templates. | Done |  | Yes
4.9:112 | 1 | The system shall save jobs so that e.g. a job history can be showed, and jobs can be rerun. | Done |  | Yes
4.9:113 | 1 | The user shall be able to monitor jobs… | Done |  | Yes
4.9:114 | 2 | The system shall provide the user with help and guidance for creating templates. | On hold | Framework for script documentation in place, more actual documentation needed
4.9:115 | 1 | The system shall provide a graphical user interface for creating and monitoring jobs. | To do | Tested implicitly, done | Yes
4.7:117 | 3 | The system shall support the possibility to integrate tactile drawings in braille. | To do
4.7:118 | 3 | The system shall support the creation of symbols lists, when characters have different meaning than normally… | To do
4.10:119 | 3 | The system shall support giving marked up mathematics code in ASCII-Math an output according to the mathematical braille code in the Netherlands. | To do